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 LICENCE
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	Site name and address (as stated on the application form or licence granted):  Old Mill Lane, Barnsley, South Yorkshire S71 1LL

	
Please ensure that the work schedules are S.M.A.R.T and appropriate timescales are provided for each activity, to fit with order of events. 


	Complete these schedules to show timings for all categories of work (mitigation and compensation measures), and to show the main construction period. The most common activities are listed here, and you can add up to 6 more if needed. Leave blank if not applicable. Enter timing by stating start and end dates, to nearest month and year (see first lines for examples). Enter comments if you need to clarify timings. For very complex schemes (e.g. high impact or phased development schemes) if additional lines are needed please do add in. This work schedule will form part of any bat licence.

E5a

	

	



WML-A13a-E5a&b (vs. March 16) (S.M.A.R.T Specific – Measurable – Achievable – Realistic – Timely)	Page 1
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	Activity
	Timing
	Comments

	Pre- development activity

	Example: Bat house creation (in advance of licence)
	Sept-14 to Nov-14
	Also put up 3 bat boxes before end of December 2015, in advance of works commencing

	Creation of standalone bat feature/s (state completed and fit for purpose if created before licensable works due to commence)
	      
	      

	Installation of bat boxes pre-development works (state completed and fit for purpose if created before licensable works due to commence)
	 Jan-23 to Feb-23
	 Install six bat boxes prior to licensable works commencing on site

	Permanent exclusion measures (e.g. use  of one-way excluders prior to permanent blocking of access points or destruction of roost)
	     
	     

	      
	      
	      

	      
	      
	      

	Mid-development activity

	Example: Capture exercise (e.g. by hand /hand-held nets, etc)
	Sept-2016
	By hand

	Pre-works inspection by Named Ecologist or Accredited Agent
	 Feb-23 to Mar-23
	 A pre-works inspection will be undertaken prior to licensable works commencing, to ensure conditions on site are as expected and to provide toolbox talks to contractors.

	Installation of protective measures (e.g. separation membranes whilst working in lofts)
	 Mar-23 to Aug-23
	 Specialist noise-reduction shields and covers (e.g. ‘Soundex Performance Curtains’) will be utilised during hydro-demolition of the parapet. It is intended that this activity will be undertaken between March 2023 and May 2023 to avoid the most sensitive hibernation and maternity periods, however allowance has been made for delays in programme.

	Disturbance by noise, illumination or vibration (please specify)
	 Mar-23 to Nov-24
	 Varying levels of disturbance through noise and vibration could occur for the duration of construction activities.

	Temporary exclusion measures (e.g. use of one-way excluders with access re-instated following works)
	      
	      

	Permanent exclusion measures (e.g. use  of one-way excluders prior to permanent blocking of access points or destruction of roost)
	      
	      

	Capture exercise (e.g. by hand / hand-held nets, etc – please state)
	      
	      

	Destructive search by soft demolition
	      
	      

	      
	      
	      

	      
	      
	      

	During development

	Example: Mechanical demolition
	Oct-2016
	Buildings X and Y will be knocked down after sign off from Named Ecologist

	Mechanical demolition of all or part of structures (once declared free of bats by Named Ecologist or Accredited Agent) – please state
	      
	      

	Construction period start and end dates
	 Mar-23 to Nov-24
	      

	Site checks and maintenance during construction
	 Mar-23 to Nov-24
	 Suitably qualified ECoW will provide a toolbox talk to contractors at the start of works on site highlighting mitigation requirements of the licence. They will oversee installation of bat boxes and undertake periodic site visits to ensure mitigation measures are being employed as necessary.

	      
	      
	      

	      
	
	

	
Post construction mitigation/compensation on ‘development’ site or other (provide details below)

	Example: Installation of access points and bat boxes
	Feb-2017
	Access points will be installed after completion of new roof structure; remaining 3 x bat boxes installed by end of this month.

	Creation of mitigation/compensation post development (e.g. installation of bat tubes, bricks, boxes, access points, etc – specify in comments section)
	      
	      

	Habitat reinstatement or restoration (following temporary impacts)
	 Jul-24 to Nov-24
	 Re-planting of woodland in temporary areas of disturbance (access routes and working areas) will be undertaken on completion of works in that part of the site. Management and monitoring of reinstated habitat will be secured through a Biodiversity Enhancement Plan (BEMP) to be approvied by the LPA. Monitoring will be undertaken in years 2, 5,10, 20 and 30 post-construction. 

	Hedgerow or woodland planting (please specify)
	      
	      

	      
	      
	      

	      
	      
	      

	

 

	
E5b) Post-development works - type a "Y" where each activity will occur for a given year and leave blank for no activity. 

	Year:
	2016
	2017
	2018
	2019
	2020
	2021
	2022
	2023
	2024
	2025
	2026
	2027

	Monitoring
	      
	      
	      
	      
	      
	      
	      
	      
	      
	 Y
	      
	 Y

	Habitat management 
	      
	      
	      
	      
	      
	      
	      
	      
	      
	      
	 Y
	      

	Site maintenance
	      
	      
	      
	      
	      
	      
	      
	      
	      
	      
	      
	      



	Year:
	2028
	2029
	2030
	2031
	2032
	2033
	2034
	2035
	2036
	2037
	2038
	2039

	Monitoring
	      
	      
	      
	      
	      
	      
	      
	      
	      
	      
	      
	      

	Habitat management 
	      
	 Y
	      
	      
	      
	      
	 Y
	      
	      
	      
	      
	      

	Site maintenance
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