## Construction Traffic_Activity
Two-way flows - Arrival and Departures |  | 2020 | [8 empty] | 2021 | [11 empty] | 2022
Ref | Activity | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
1 | Mobilisation
1 | HGVs / month |  |  |  |  | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| LGVs & Cars / month |  |  |  |  | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Enabling works
2 | HGVs / month | [5 empty] | 20 | 100 | 100 | 80 | 0 | 0 | 0 | 0 | 0 | 0
| LGVs & Cars / month | [5 empty] | 250 | 500 | 500 | 400 | 0 | 0 | 0 | 0 | 0 | 0
3 | Access Road
| HGVs / month |  |  |  |  | 640 | 640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| LGVs & Cars / month |  |  |  |  | 520 | 520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Trans Pennine Trail Diversion
| HGVs / month |  |  | 0 |  |  |  |  | 704 | 1344 | 832 | 0 | 0 | 0 | 0 | 0
| LGVs & Cars / month |  |  | 0 |  |  |  |  | 572 | 1092 | 676 | 0 | 0 | 0 | 0 | 0
5 | Permanent Bridge
| HGVs / month |  |  | 0 | 0 | 0 |  | 50 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0
| LGVs & Cars / month |  |  | 0 | 0 | 0 |  | 50 | 230 | 230 | 0 | 0 | 0 | 0 | 0 | 0
6 | Temporary Bridge
| HGVs / month |  |  | 0 | 0 | 0 |  |  |  | 200 | 100 | 0 | 0 | 0 | 0 | 0
| LGVs & Cars / month |  |  | 0 | 0 | 0 |  |  |  | 200 | 100 | 0 | 0 | 0 | 0 | 0
7 | Cable Installation
| HGVs / month | [5 empty] | 0 |  |  |  | 178 | 174 | 172 | 252 | 174 | 164 | 84 | 80
| LGVs & Cars / month | [5 empty] | 0 |  |  |  | 320 | 880 | 1040 | 800 | 880 | 880 | 680 | 640
8 | Construction of SEC
| HGVs / month |  |  |  | 0 | 0 | 0
| LGVs & Cars / month |  |  |  | 0 | 0 | 0 | 272 | 336 | 320 | 352 | 320 | 352 | 320 | 304 | 320 | 320 | 320
9 | Removal of OHL
| HGVs / month | [9 empty] | 0 | 0 | 250 | 250 | 270 | 270 | 240 | 240 | 180 | 180
| LGVs & Cars / month | [9 empty] | 0 | 0 | 608 | 608 | 704 | 736 | 640 | 704 | 528 | 528
10 | Reinstatement & Demobilisation
| HGVs / month | [9 empty] | 0 | 0
| LGVs & Cars / month | [9 empty] | 0 | 0 | [6 empty] | 572 | 1092 | 1092 | 520 | 520 | 520
11 | General Traffic to / from Site
| HGVs / month |  |  | 40 | 42 | 40 | 46 | 42 | 42 | 46 | 42 | 40 | 44 | 40 | 44 | 40 | 38 | 44 | 46 | 40 | 44 | 44 | 42 | 42 | 10
| LGVs & Cars / month |  |  | 320 | 336 | 320 | 368 | 336 | 336 | 368 | 336 | 320 | 352 | 320 | 352 | 320 | 304 | 352 | 368 | 320 | 352 | 352 | 336 | 336 | 320
#REF! | #REF!
| HGVs / month |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| LGVs & Cars / month |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF!
| HGVs / month |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| LGVs & Cars / month |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF!
| HGVs / month |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| LGVs & Cars / month |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF!
| HGVs / month |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| LGVs & Cars / month |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF!
| HGVs / month |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| LGVs & Cars / month |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF!
| HGVs / month |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| LGVs & Cars / month |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
HGVs / month (two-way movements) |  |  |  | 40 | 42 | 680 | 786 | 192 | 946 | 1770 | 1152 | 214 | 466 | 542 | 488 | 474 | 362 | 364 | 226 | 220 | 44 | 44 | 42 | 42 | 10 | 9146
LGVs & Cars / month (two-way movements) |  |  |  | 320 | 336 | 840 | 1538 | 1158 | 1974 | 2610 | 1784 | 1520 | 2352 | 2048 | 2240 | 2256 | 1944 | 2016 | 1468 | 1940 | 1444 | 872 | 856 | 856 | 320 | 32692
Total Construction Traffic Vehicles / month (two-way movements) |  |  |  | 360 | 378 | 1520 | 2324 | 1350 | 2920 | 4380 | 2936 | 1734 | 2818 | 2590 | 2728 | 2730 | 2306 | 2380 | 1694 | 2160 | 1488 | 916 | 898 | 898 | 330 | 41838
HGVs / day (two-way movements) |  |  |  | 2 | 2.1 | 34 | 39.3 | 9.6 | 47.3 | 88.5 | 57.6 | 10.7 | 23.3 | 27.1 | 24.4 | 23.7 | 18.1 | 18.2 | 11.3 | 11 | 2.2 | 2.2 | 2.1 | 2.1 | 0.5 | 457.3
LGVs & Cars / day (two-way movements) |  |  |  | 16 | 16.8 | 42 | 76.9 | 57.9 | 98.7 | 130.5 | 89.2 | 76 | 117.6 | 102.4 | 112 | 112.8 | 97.2 | 100.8 | 73.4 | 97 | 72.2 | 43.6 | 42.8 | 42.8 | 16 | 1634.6
Total Construction Traffic Vehicles / day (two-way movements) |  | 0 | 0 | 18 | 18.9 | 76 | 116.2 | 67.5 | 146 | 219 | 146.8 | 86.7 | 140.9 | 129.5 | 136.4 | 136.5 | 115.3 | 119 | 84.7 | 108 | 74.4 | 45.8 | 44.9 | 44.9 | 16.5 | 2091.9
[28 empty] | 20 | Days a month
| Initial stage (site mobilisation) | [9 empty] | 10 | [16 empty] | 40 | 2 way movements a month
| Site team - 5 | [9 empty] | 200
| Trench excavation and prep | [9 empty] | 168 | 168 | 168
| 1 Excavation team - 8 | [9 empty] | 120 | 320 | 320 | [12 empty] | HGV | LGV
| Cable Pulling | [10 empty] | 2 | [13 empty] | 188 | 6
| Cable Installtion team - 10 | [10 empty] | 400 | 400 | [13 empty] | 12603
| Joint Bays & Jointing | [10 empty] | 4 | 4 | 4 | [11 empty] | 779 | 10446
| 1 Jointing team - 8 | [10 empty] | 160 | 320 | 160
| trench Reinstatement | [12 empty] | 80 | [11 empty] | 967 | 23055
| 1 Excavation team - 8 | [12 empty] | 320
| Trench excavation and prep | [12 empty] | 168 | 168 | 160 | [9 empty] | 0 | 0
| 1 Excavation team - 8 | [12 empty] | 320 | 320 | 160
| Cable Pulling | [13 empty] | 2 | 0 | 0
| Cable Installation team - 10 | [13 empty] | 400 | 400 | 200
| Joint Bays & Jointing | [13 empty] | 4 | 4 | 4
| 1 Jointing team - 8 | [13 empty] | 160 | 320 | 160
| trench Reinstatement | [15 empty] | 80 | 80
| 1 Excavation team - 8 | [15 empty] | 320 | 320
| Testing and commisioning | [16 empty] | 0
| Site team + testers - 8 | [16 empty] | 320
| HGVs / month (two-way movements) | [9 empty] | 178 | 174 | 172 | 252 | 174 | 164 | 84 | 80
| LGVs & Cars / month (two-way movements) | [9 empty] | 320 | 880 | 1040 | 800 | 880 | 880 | 680 | 640
| AIL Movements - 18 x drums for power cable | [10 empty] | 5 | 4 |  | 5 | 4
HGV Movements
Trench excavation
For standard trench (excavation per metre) = 1.5 m width x 1.25 m deep = 1.875 m3 x 2
To be stored locally (per metre of trench for both trenches) 1.5 m x 0.75 = 1.125 m3 x 2
CBS to be delivered daily 1.5 m x 0.5 = 0.75 m3 x 45 = 33.75 m3 (per trench per day) = 4 lorry movements "in"
Spoil to be removed daily = 33.75 m3 (per trench per day) - Same lorry out
Deliveries to site:
| Power cable ducts 1.8 km x 6 = 10.8 km (assume 18 x deliveries) |  | 18
| F.O. cable ducts 1.8 x 2 = 3.6 km (assume 2 x deliveries) |  | 2
| 2 x drums for fibre optic cable. (2 x deliveries) |  | 2
| 6 x terminations + link-boxes (assume 2 x lorry deliveries) |  | 2
| 18 x straight-joints (assume 6 lorry deliveries) |  | 6
| 4 x Link-pillars (assume 2 lorry deliveries) |  | 2
32

## Peak Construction Traffic
Estimated highest construction traffic flows on various road sections in 2021
ATC | Location | Direction | Highest estimated daily construction traffic flows (2021)
|  |  | Peak Hour (0800-9000) |  |  |  | 12hr (0700-1900) |  |  |  | 18hr (0600-0000) |  |  |  | 24hr (0000-0000) |  |  |  | Speed (85 %ile)
|  |  | LGV | HGV | Total | %HGV | LGV | HGV | Total | %HGV | LGV | HGV | Total | %HGV | LGV | HGV | Total | %HGV | Mph
1&2 | A628 | E/B | 3 | 2 | 5 | 40% | 26 | 20 | 46 | 43.48% | 26 | 20 | 46 | 43.48% | 26 | 20 | 46 | 43.48% | 50.5
|  | W/B | 3 | 2 | 5 | 40% | 26 | 20 | 46 | 43.48% | 26 | 20 | 46 | 43.48% | 26 | 20 | 46 | 43.48% | 55.5
|  | 2-Way | 6 | 4 | 10 | 40% | 52 | 40 | 92 | 43.48% | 52 | 40 | 92 | 43.48% | 52 | 40 | 92 | 43.48%
3 | Goddard Lane | N/B | 5 | 4 | 9 | 44.44% | 50 | 40 | 90 | 44.44% | 50 | 40 | 90 | 44.44% | 50 | 40 | 90 | 44.44% | 57.675
|  | S/B | 5 | 4 | 9 | 44.44% | 50 | 40 | 90 | 44.44% | 50 | 40 | 90 | 44.44% | 50 | 40 | 90 | 44.44% | 46.55
|  | 2-Way | 10 | 8 | 18 | 44.44% | 100 | 80 | 180 | 44.44% | 100 | 80 | 180 | 44.44% | 100 | 80 | 180 | 44.44%
4 | A616 Whams Road | N/B | 0 | 1 | 1 | 100% | 5 | 4 | 9 | 44.44% | 5 | 4 | 9 | 44.44% | 5 | 4 | 9 | 44.44% | N/A
|  | S/B | 0 | 1 | 1 | 100% | 5 | 4 | 9 | 44.44% | 5 | 4 | 9 | 44.44% | 5 | 4 | 9 | 44.44% | N/A
|  | 2-Way | 0 | 2 | 2 | 100% | 10 | 8 | 18 | 44.44% | 10 | 8 | 18 | 44.44% | 10 | 8 | 18 | 44.44%
5 | Windle Edge north | N/B | 5 | 4 | 9 | 44.44% | 50 | 40 | 90 | 44.44% | 50 | 40 | 90 | 44.44% | 50 | 40 | 90 | 44.44% | 20
|  | S/B | 5 | 4 | 9 | 44.44% | 50 | 40 | 90 | 44.44% | 50 | 40 | 90 | 44.44% | 50 | 40 | 90 | 44.44% | 20
|  | 2-Way | 10 | 8 | 18 | 44.44% | 100 | 80 | 180 | 44.44% | 100 | 80 | 180 | 44.44% | 100 | 80 | 180 | 44.44%
6 | Brook Hill Lane | N/B | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 43.535
|  | S/B | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 30.05
|  | 2-Way | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0%
7 | Whams Road | N/B | 0 | 120 | 120 | 100% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 57.565
|  | S/B | 0 | 120 | 120 | 100% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 58.29
|  | 2-Way | 0 | 240 | 240 | 100% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0%
| B6106 Bents Road | E/B | bar: Total
W/B | bar: Total
2-Way | bar: LGV to Total
It is assumed that a speed limit restriction (20mph) will be applied to the section of Goddard Lane/Windle Edge between AP2 and AP7

## MS-Construction Traffic_Activit
Two-way flows - Arrival and Departures |  | 2020 | [8 empty] | 2021 | [11 empty] | 2022 | [6 empty] | 2020 | [8 empty] | 2021 | [11 empty] | 2022 |  |  |  |  | 2020 | [8 empty] | 2021 | [11 empty] | 2022
Ref | Activity | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr |  |  |  | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Mar |  | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
1 | Mobilisation
1 | HGVs / month | 0 | 0 | 0 | 0 | 0 | 50.4 | 0 | 0 | 0 | 0 | 0 | 0 | 10.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61.2 |  | 1 | [5 empty] | 42 | [6 empty] | 9
| LGVs & Cars / month | 0 | 0 | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6 | [7 empty] | 3
2 | Enabling works | [25 empty] | 0
2 | HGVs / month | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | [7 empty] | 5 | [28 empty] | 6.6667 | 6.6667 | 6.6667 | [14 empty] | 20
| LGVs & Cars / month | 0 | 0 | 0 | 0 | 0 | 388.8 | 0 | 0 | 252.4 | 252.4 | 252.4 | 0 | 0 | 0 | 0 | 108 | 108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1362 | [7 empty] | 324 |  |  | 210 | 210 | 210 |  |  |  |  | 90 | 90 | [17 empty] | 0.33333 | 0.33333 | 0.33333 | [14 empty] | 1
3 | Access Road - Predominantly AP07 | [25 empty] | 0
| HGVs / month | 0 | 0 | 0 | 0 | 136 | 136 | 136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 408 | [6 empty] | 0 | 0 | [24 empty] | 113.3333 | 113.3333 | 113.3333 | [18 empty] | 340
| LGVs & Cars / month | 0 | 0 | 0 | 0 | 216 | 216 | 216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 648 | [6 empty] | 180 | 180 | 180 | [23 empty] | 0 | 0 | 0 | [18 empty] | 0
4 | Trans Pennine Trail Diversion - Predominantly AP07 | [25 empty] | 0
| HGVs / month | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162 | 162 | 162 | 162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 648 | [9 empty] | 0 | 0 | 0 | 0 | [22 empty] | 135 | 135 | 135 | 135 | [14 empty] | 540
| LGVs & Cars / month | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 324 | 324 | 324 | 324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1296 | [9 empty] | 270 | 270 | 270 | 270 | [22 empty] | 0 | 0 | 0 | 0 | [14 empty] | 0
5 | Permanent Bridge - Access Split Between AP05 & AP07 | [25 empty] | 0
| HGVs / month | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 8.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.2 | [9 empty] | 0 | 2 | [24 empty] | 5 | 5 | [16 empty] | 10
| LGVs & Cars / month | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270 | 270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270 | [9 empty] | 225 | 225 | [42 empty] | 0
6 | Temporary Bridge - Access Split Between AP05 & AP07 | [25 empty] | 0
| HGVs / month | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.8 | 16.8 | 16.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25.2 | [9 empty] | 0 | 0 | 0 | [23 empty] | 14 | 14 | 14 | [15 empty] | 42
| LGVs & Cars / month | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 216 | 324 | 216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 398 | [9 empty] | 180 | 270 | 180 | [41 empty] | 0
7 | Cable Installation - Predominantly AP05 | [25 empty] | 0
| HGVs / month | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222.84 | 227.04 | 227.7257 | 227.7257 | 227.7257 | 223.5257 | 223.5257 | 230.7257 | 230.7257 | 222.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2264.4 | [10 empty] | 3.5 | 4.0714 | 4.0714 | 4.0714 | 0.57143 | 0.57143 | 6.5714 | 6.5714 | [17 empty] | 185.7 | 185.7 | 185.7 | 185.7 | 185.7 | 185.7 | 185.7 | 185.7 | 185.7 | 185.7 | [8 empty] | 1857
| LGVs & Cars / month | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158.88 | 424.08 | 464.88 | 306.48 | 306.48 | 41.28 | 41.28 | 338.88 | 338.88 | 125.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2546.4 | [9 empty] | 132 | 353 | 387 | 255 | 255 | 34 | 34 | 282 | 282 | 104 | [16 empty] | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | [8 empty] | 4
8 | Construction of SEC - Access Split Between AP05 & AP07 | [25 empty] | 0
| HGVs / month | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.7333 | 9.7333 | 9.7333 | 9.7333 | 9.7333 | 9.7333 | 9.7333 | 9.7333 | 9.7333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43.8 | [36 empty] | 8.1111 | 8.1111 | 8.1111 | 8.1111 | 8.1111 | 8.1111 | 8.1111 | 8.1111 | 8.1111 | [8 empty] | 73
| LGVs & Cars / month | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24.8 | 24.8 | 24.8 | 24.8 | 24.8 | 24.8 | 24.8 | 24.8 | 24.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111.6 | [10 empty] | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | [17 empty] | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 0.66667 | [8 empty] | 6
9 | Removal of OHL - Split Over AP02, AP03, AP04, AP06 & AP07 | [25 empty] | 0
| HGVs / month | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280.4571 | 122.0571 | 118.4571 | 118.4571 | 118.4571 | 118.4571 | 100.6667 | 4.8 | 0 | 0 | 0 | 0 | 327.2698 | [15 empty] | 219.7143 | 87.7143 | 84.7143 | 84.7143 | 84.7143 | 84.7143 | 69.8889 | 4 | [18 empty] | 14 | 14 | 14 | 14 | 14 | 14 | 14 | [5 empty] | 100
| LGVs & Cars / month | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 492.6857 | 348.6857 | 300.6857 | 300.6857 | 300.6857 | 300.6857 | 390.6857 | 90 | 0 | 0 | 0 | 0 | 841.6 | [15 empty] | 410 | 290 | 250 | 250 | 250 | 250 | 325 | 75 | [18 empty] | 0.57143 | 0.57143 | 0.57143 | 0.57143 | 0.57143 | 0.57143 | 0.57143 | [5 empty] | 4
10 | Reinstatement & Demobilisation - Access Split Between AP05 & AP07 | [25 empty] | 0
| HGVs / month | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 319.8 | 277.8 | 277.8 | 283.8 | 19.2 | 589.2 |  | 1 | [20 empty] | 35 |  |  | 5 | 16 | [21 empty] | 231.5 | 231.5 | 231.5 | 231.5 |  | 926
| LGVs & Cars / month | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 363.6 | 846 | 846 | 604.8 | 0 | 1330.2 | [22 empty] | 303 | 705 | 705 | 504 | [27 empty] | 0
11 | General Traffic to / from Site - Access Split Between AP05 & AP07 | [25 empty] | 0
| HGVs / month | 1 | 3 | 4.8 | 4.8 | 4.8 | 4.8 | 4.8 | 4.8 | 4.8 | 4.8 | 4.8 | 4.8 | 4.8 | 4.8 | 4.8 | 4.8 | 4.8 | 4.8 | 4.8 | 4.8 | 4.8 | 0 | 0 | 0 | 0 | 47.6 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
| LGVs & Cars / month | 60 | 120 | 200 | 200 | 500 | 1053.6 | 1053.6 | 1053.6 | 1053.6 | 1053.6 | 1063.2 | 1125.6 | 1125.6 | 1125.6 | 1125.6 | 1125.6 | 882.24 | 782.4 | 782.4 | 782.4 | 782.4 | 782.4 | 782.4 | 741.6 | 0 | 9678.72 |  |  | 832 | 878 | 878 | 878 | 878 | 878 | 878 | 878 | 878 | 878 | 886 | 938 | 938 | 938 | 938 | 938 | 735.2 | 652 | 652 | 652 | 652 | 652 | 652 | 618
#REF! | #REF!
| HGVs / month |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
| LGVs & Cars / month |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF!
| HGVs / month |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
| LGVs & Cars / month |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF!
| HGVs / month |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
| LGVs & Cars / month |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF!
| HGVs / month |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
| LGVs & Cars / month |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF!
| HGVs / month |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
| LGVs & Cars / month |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF!
| HGVs / month |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
| LGVs & Cars / month |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
HGVs / month (two-way movements) |  | 1 | 3 | 4.8 | 4.8 | 140.8 | 197.2 | 140.8 | 412.44 | 436.7733 | 429.059 | 412.259 | 242.259 | 248.859 | 518.5162 | 367.3162 | 363.7162 | 355.8305 | 123.2571 | 123.2571 | 105.4667 | 329.4 | 277.8 | 277.8 | 283.8 | 19.2 |  | 5819.4095
LGVs & Cars / month (two-way movements) |  | 70 | 130 | 210 | 210 | 716 | 1662 | 1269.6 | 2022.48 | 2672.88 | 2335.68 | 1970.88 | 1456.88 | 1191.68 | 1684.3657 | 1837.9657 | 1897.9657 | 1441.0057 | 1083.0857 | 1083.0857 | 1173.0857 | 1236 | 1628.4 | 1628.4 | 1346.4 | 0 |  | 31957.84 | 2 | 4 | 4 | 4 | 4 | 4 | 51 | 4 | 4 | 9.5 | 8.0714 | 8.0714 | 8.0714 | 13.5714 | 224.2857 | 98.2857 | 95.2857 | 88.7143 | 88.7143 | 88.7143 | 73.8889 | 43 | 0 | 0 | 5 | 16 | 0 | 0 | 0 | 0 | 0 | 113.3333 | 113.3333 | 113.3333 | 339.7 | 354.4778 | 349.4778 | 335.4778 | 193.8111 | 193.8111 | 207.8111 | 207.8111 | 207.8111 | 207.8111 | 14 | 14 | 14 | 231.5 | 231.5 | 231.5 | 231.5 | 0
Total Construction Traffic Vehicles / month (two-way movements) |  | 71 | 133 | 214.8 | 214.8 | 856.8 | 1859.2 | 1410.4 | 2434.92 | 3109.6533 | 2764.739 | 2383.139 | 1699.139 | 1440.539 | 2202.8819 | 2205.2819 | 2261.6819 | 1796.8362 | 1206.3429 | 1206.3429 | 1278.5524 | 1565.4 | 1906.2 | 1906.2 | 1630.2 | 19.2 |  | 37777.2495 | 0 | 832 | 878 | 878 | 878 | 1058 | 1385 | 1058 | 1685 | 2226 | 1945 | 1641 | 1213 | 992 | 1402 | 1530 | 1580 | 1199.2 | 902 | 902 | 977 | 1030 | 1357 | 1357 | 1122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 1.4 | 1.4 | 1.4 | 1.0667 | 1.0667 | 1.6381 | 1.6381 | 1.6381 | 1.6381 | 0.57143 | 0.57143 | 0.57143 | 0 | 0 | 0 | 0 | 0
HGVs / day (two-way movements) |  | 0.05 | 0.15 | 0.24 | 0.24 | 7.04 | 9.86 | 7.04 | 20.622 | 21.8387 | 21.453 | 20.613 | 12.113 | 12.443 | 25.9258 | 18.3658 | 18.1858 | 17.7915 | 6.1629 | 6.1629 | 5.2733 | 16.47 | 13.89 | 13.89 | 14.19 | 0.96 |  | 290.9705 |  | Contingency |  |  |  |  | 20%
LGVs & Cars / day (two-way movements) |  | 3.5 | 6.5 | 10.5 | 10.5 | 35.8 | 83.1 | 63.48 | 101.124 | 133.644 | 116.784 | 98.544 | 72.844 | 59.584 | 84.2183 | 91.8983 | 94.8983 | 72.0503 | 54.1543 | 54.1543 | 58.6543 | 61.8 | 81.42 | 81.42 | 67.32 | 0 |  | 1597.892
Total Construction Traffic Vehicles / day (two-way movements) |  | 3.55 | 6.65 | 10.74 | 10.74 | 42.84 | 92.96 | 70.52 | 121.746 | 155.4827 | 138.237 | 119.157 | 84.957 | 72.027 | 110.1441 | 110.2641 | 113.0841 | 89.8418 | 60.3171 | 60.3171 | 63.9276 | 78.27 | 95.31 | 95.31 | 81.51 | 0.96 |  | 1888.8625
Notes:
Material movements based on quantities provided in CIT document
Materials remaining on site excluded
Staff movements allow for access to site plus movements around site for site personnel only
Staff movements include allowance for 4 nr National Grid staff on average
Operative movements split evenly over approx. duration or works
Contingency of 20% allowed against all items to account for unknowns / revisions
Revisions
rev C | Material movements for Access Road rein moved to item 10
rev C | Material movements for TPT rein moved to item 10
| Key: | HGV's |  | LGVs & Cars
| AP05 | 3395.8698 |  | 16542.12
| AP06 | 197.2698 |  | 504.6
| AP07 | 1638 |  | 13395.52
| AP04 | 196.2698 |  | 505.6
| AP02 | 196 |  | 505
| AP03 | 196 |  | 505
| Total | 5819.4095 |  | 31957.84

## Staff
275kV Bustleholm - Nechells 1 & 2 Cable Replacement
National Grid Electricity Transmission Plc
Staff
Role | Name | 2019-10-07 | 2019-10-14 | 2019-10-21 | 2019-10-28 | 2019-11-04 | 2019-11-11 | 2019-11-18 | 2019-11-25 | 2019-12-02 | 2019-12-09 | 2019-12-16 | 2019-12-23 | 2019-12-30 | 2020-01-06 | 2020-01-13 | 2020-01-20 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 | 2020-03-30 | 2020-04-06 | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08 | 2020-06-15 | 2020-06-22 | 2020-06-29 | 2020-07-06 | 2020-07-13 | 2020-07-20 | 2020-07-27 | 2020-08-03 | 2020-08-10 | 2020-08-17 | 2020-08-24 | 2020-08-31 | 2020-09-07 | 2020-09-14 | 2020-09-21 | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-10-26 | 2020-11-02 | 2020-11-09 | 2020-11-16 | 2020-11-23 | 2020-11-30 | 2020-12-07 | 2020-12-14 | 2020-12-21 | 2020-12-28 | 2021-01-04 | 2021-01-11 | 2021-01-18 | 2021-01-25 | 2021-02-01 | 2021-02-08 | 2021-02-15 | 2021-02-22 | 2021-03-01 | 2021-03-08 | 2021-03-15 | 2021-03-22 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 2021-04-19 | 2021-04-26 | 2021-05-03 | 2021-05-10 | 2021-05-17 | 2021-05-24 | 2021-05-31 | 2021-06-07 | 2021-06-14 | 2021-06-21 | 2021-06-28 | 2021-07-05 | 2021-07-12 | 2021-07-19 | 2021-07-26 | 2021-08-02 | 2021-08-09 | 2021-08-16 | 2021-08-23 | 2021-08-30 | 2021-09-06 | 2021-09-13 | 2021-09-20 | 2021-09-27 | 2021-10-04 | 2021-10-11 | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185
Project Governance
Operations Director | Ian Maddison | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
Senior Commercial Director | Mark Hopkin | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
Project Management Staff
SeniorProject Manager | Ian Burns | bar: 1 to 143
Planner | Sophie Lavell | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
Technical Support - Cables | Martin Clarke | 1: 0.2; 2: 0.2; 3: 0.2; 4: 0.2; 5: 0.2; 6: 0.2; 7: 0.2; 8: 0.2; 9: 0.2; 10: 0.2; 11: 0.2; 12: 0.2; 13: 0.2; 14: 0.2; 15: 0.2; 16: 0.2; 17: 0.2; 18: 0.2; 19: 0.2; 20: 0.2; 21: 0.2; 22: 0.2; 23: 0.2; 24: 0.2; 25: 0.2; 26: 0.2; 27: 0.2; 28: 0.2; 29: 0.2; 30: 0.2; 31: 0.2; 32: 0.2; 33: 0.2; 34: 0.2; 35: 0.2; 36: 0.2; 37: 0.2; 38: 0.2; 39: 0.2; 40: 0.2; 41: 0.2; 42: 0.2; 43: 0.2; 44: 0.2; 45: 0.2; 46: 0.2; 47: 0.2; 48: 0.2; 49: 0.2; 50: 0.2; 51: 0.2; 52: 0.2; 53: 0.2; 54: 0.2; 55: 0.2; 56: 0.2; 57: 0.2; 58: 0.2; 59: 0.2; 60: 0.2; 61: 0.2; 62: 0.2; 63: 0.2; 64: 0.2; 65: 0.2; 66: 0.2; 67: 0.2; 68: 0.2; 69: 0.2; 70: 0.2; 71: 0.2; 72: 0.2; 73: 0.2; 74: 0.2; 75: 0.2; 76: 0.2; 77: 0.2; 78: 0.2; 79: 0.2; 80: 0.2; 81: 0.2; 82: 0.2; 83: 0.2; 84: 0.2; 85: 0.2; 86: 0.2; 87: 0.2; 88: 0.2; 89: 0.2; 90: 0.2; 91: 0.2; 92: 0.2; 93: 0.2; 94: 0.2; 95: 0.2; 96: 0.2; 97: 0.2
Technical Support - OHL | Jas Harrar | 1: 0.2; 2: 0.2; 3: 0.2; 4: 0.2; 5: 0.2; 6: 0.2; 7: 0.2; 8: 0.2; 9: 0.2; 10: 0.2; 11: 0.2; 12: 0.2; 13: 0.2; 14: 0.2; 15: 0.2; 16: 0.2; 17: 0.2; 18: 0.2; 19: 0.2; 20: 0.2; 21: 0.2; 22: 0.2; 23: 0.2; 24: 0.2; 25: 0.2; 26: 0.2; 27: 0.2; 28: 0.2; 29: 0.2; 30: 0.2; 31: 0.2; 32: 0.2; 33: 0.2; 34: 0.2; 35: 0.2; 36: 0.2; 37: 0.2; 38: 0.2; 39: 0.2; 40: 0.2; 41: 0.2; 42: 0.2; 43: 0.2; 44: 0.2; 45: 0.2; 46: 0.2; 47: 0.2; 48: 0.2; 49: 0.2; 50: 0.2; 51: 0.2; 52: 0.2; 53: 0.2; 54: 0.2; 55: 0.2; 56: 0.2; 57: 0.2; 58: 0.2; 59: 0.2; 60: 0.2; 61: 0.2; 62: 0.2; 63: 0.2; 64: 0.2; 65: 0.2; 66: 0.2; 67: 0.2; 68: 0.2; 69: 0.2; 70: 0.2; 71: 0.2; 72: 0.2; 73: 0.2; 74: 0.2; 75: 0.2; 76: 0.2; 77: 0.2; 78: 0.2; 79: 0.2; 80: 0.2; 81: 0.2; 82: 0.2; 83: 0.2; 84: 0.2; 85: 0.2; 86: 0.2; 87: 0.2; 88: 0.2; 89: 0.2; 90: 0.2; 91: 0.2; 92: 0.2; 93: 0.2; 94: 0.2; 95: 0.2; 96: 0.2; 97: 0.2
Engineering & Technical Staff
TP137 Site Manager | Alan Gough | bar: 1 to 135
Works Manager | David Barker | bar: 25 to 135
Senior Civils Engineer | Andrew Swain | bar: 25 to 130
Setting Out Engineer | Thomas Cimatti | bar: 25 to 97
TWC/Deputy Site Manager | Marc Pinckard | bar: 25 to 130
Section Foreman | TBC | bar: 25 to 130
Section Foreman | TBC | bar: 25 to 97
Section Foreman TBC
OHL Engineer | Sean Barker | bar: 75 to 131
Stakeholder/Community Engagement/Wayleaves | RSK | bar: 1 to 131
Cable Manager | Trevor McGhee | 29: 0.4; 30: 0.4; 31: 0.4; 32: 0.4; 33: 0.4; 34: 0.4; 35: 0.4; 36: 0.4; 37: 0.4; 38: 0.4; 39: 0.4; 40: 0.4; 41: 0.4; 42: 0.4; 43: 0.4; 44: 0.4; 45: 0.4; 46: 0.4; 47: 0.4; 48: 0.4; 49: 0.4; 50: 0.4; 51: 0.4; 52: 0.4; 53: 0.4; 54: 0.4; 55: 0.4; 56: 0.4; 57: 0.4; 58: 0.4; 59: 0.4; 60: 0.4; 61: 0.4; 62: 0.4; 63: 0.4; 64: 0.4; 65: 0.4; 66: 0.4; 67: 0.4; 68: 0.4; 69: 0.4; 70: 0.4; 71: 0.4; 72: 0.4; 73: 0.4; 74: 0.4; 75: 0.4; 76: 0.4; 77: 0.4; 78: 0.4; 79: 0.4; 80: 0.4; 81: 0.4; 82: 0.4; 83: 0.4; 84: 0.4; 85: 0.4; 86: 0.4; 87: 0.4; 88: 0.4; 89: 0.4; 90: 0.4; 91: 0.4; 92: 0.4; 93: 0.4; 94: 0.4; 95: 0.4; 96: 0.4; 97: 0.4
Commercial/Financial Staff
Senior Commercial Manager | Andy Tweed | [20 empty] | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6
Senior Quantity Surveyor | bar: 1 to 97
Assistant Quantity Surveyor | bar: 29 to 143
Buyer |  | 1: 0.4; 2: 0.4; 3: 0.4; 4: 0.4; 5: 0.4; 6: 0.4; 7: 0.4; 8: 0.4; 9: 0.4; 10: 0.4; 11: 0.4; 12: 0.4; 13: 0.4; 14: 0.4; 15: 0.4; 16: 0.4; 17: 0.4; 18: 0.4; 19: 0.4; 20: 0.4; 21: 0.4; 22: 0.4; 23: 0.4; 24: 0.4; 25: 0.4; 26: 0.4; 27: 0.4; 28: 0.4; 29: 0.4; 30: 0.4; 31: 0.4; 32: 0.4; 33: 0.4; 34: 0.4; 35: 0.4; 36: 0.4; 37: 0.4; 38: 0.4; 39: 0.4; 40: 0.4; 41: 0.4; 42: 0.4; 43: 0.4; 44: 0.4; 45: 0.4; 46: 0.4; 47: 0.4; 48: 0.4; 49: 0.4; 50: 0.4; 51: 0.4; 52: 0.4; 53: 0.4; 54: 0.4; 55: 0.4; 56: 0.4; 57: 0.4; 58: 0.4; 59: 0.4; 60: 0.4; 61: 0.4; 62: 0.4; 63: 0.4; 64: 0.4; 65: 0.4; 66: 0.4; 67: 0.4; 68: 0.4; 69: 0.4; 70: 0.4; 71: 0.4; 72: 0.4; 73: 0.4; 74: 0.4; 75: 0.4; 76: 0.4; 77: 0.4; 78: 0.4; 79: 0.4; 80: 0.4; 81: 0.4; 82: 0.4; 83: 0.4; 84: 0.4; 85: 0.4; 86: 0.4; 87: 0.4; 88: 0.4; 89: 0.4; 90: 0.4; 91: 0.4; 92: 0.4; 93: 0.4; 94: 0.4; 95: 0.4; 96: 0.4; 97: 0.4
Cost Manager |  | 29: 0.2; 30: 0.2; 31: 0.2; 32: 0.2; 33: 0.2; 34: 0.2; 35: 0.2; 36: 0.2; 37: 0.2; 38: 0.2; 39: 0.2; 40: 0.2; 41: 0.2; 42: 0.2; 43: 0.2; 44: 0.2; 45: 0.2; 46: 0.2; 47: 0.2; 48: 0.2; 49: 0.2; 50: 0.2; 51: 0.2; 52: 0.2; 53: 0.2; 54: 0.2; 55: 0.2; 56: 0.2; 57: 0.2; 58: 0.2; 59: 0.2; 60: 0.2; 61: 0.2; 62: 0.2; 63: 0.2; 64: 0.2; 65: 0.2; 66: 0.2; 67: 0.2; 68: 0.2; 69: 0.2; 70: 0.2; 71: 0.2; 72: 0.2; 73: 0.2; 74: 0.2; 75: 0.2; 76: 0.2; 77: 0.2; 78: 0.2; 79: 0.2; 80: 0.2; 81: 0.2; 82: 0.2; 83: 0.2; 84: 0.2; 85: 0.2; 86: 0.2; 87: 0.2; 88: 0.2; 89: 0.2; 90: 0.2; 91: 0.2; 92: 0.2; 93: 0.2; 94: 0.2; 95: 0.2; 96: 0.2; 97: 0.2
Administrative/Clerical
Document Controller / Admin | bar: 1 to 143
Admin | bar: 27 to 97
SHESQ
Environmental Advisor | Claire Briggs | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
Safety Advisor | Martin Smith | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Quality Advisor | Dai Parry | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
Environmental Consultant | bar: 29 to 97
Testing and Commissioning
TP141 Comm Engineer | TBC | bar: 1 to 8
Design
Design Manager |  | 1: 1; 2: 1; 3: 1; 4: 1; 5: 1; 6: 1; 7: 1; 8: 1; 9: 1; 10: 1; 11: 1; 12: 1; 13: 1; 14: 1; 15: 1; 16: 1; 17: 1; 18: 1; 19: 1; 20: 1; 21: 1; 22: 1; 23: 1; 24: 1; 25: 1; 26: 1; 27: 1; 28: 1; 29: 0.4; 30: 0.4; 31: 0.4; 32: 0.4; 33: 0.4; 34: 0.4; 35: 0.4; 36: 0.4; 37: 0.4; 38: 0.4; 39: 0.4; 40: 0.4; 41: 0.4; 42: 0.4; 43: 0.4; 44: 0.4; 45: 0.4; 46: 0.4; 47: 0.4; 48: 0.4; 49: 0.4; 50: 0.4; 51: 0.4; 52: 0.4; 53: 0.4; 54: 0.4; 55: 0.4; 56: 0.4; 57: 0.4; 58: 0.4; 59: 0.4; 60: 0.4; 61: 0.4; 62: 0.4; 63: 0.4; 64: 0.4; 65: 0.4; 66: 0.4; 67: 0.4; 68: 0.4; 69: 0.4; 70: 0.4; 71: 0.4; 72: 0.4; 73: 0.4; 74: 0.4; 75: 0.4; 76: 0.4; 77: 0.4; 78: 0.4; 79: 0.4; 80: 0.4; 81: 0.4; 82: 0.4; 83: 0.4; 84: 0.4; 85: 0.4; 86: 0.4; 87: 0.4; 88: 0.4; 89: 0.4; 90: 0.4; 91: 0.4; 92: 0.4; 93: 0.4; 94: 0.4; 95: 0.4; 96: 0.4; 97: 0.4
|  | 10.5 | 10.5 | 10.5 | 10.5 | 10.5 | 10.5 | 10.5 | 10.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 10.1 | 10.1 | 10.1 | 10.1 | 16.1 | 16.1 | 17.1 | 17.1 | 19.3 | 19.3 | 19.3 | 19.3 | 19.3 | 19.3 | 19.3 | 19.3 | 19.3 | 19.3 | 19.3 | 19.3 | 19.3 | 19.3 | 19.3 | 19.3 | 19.3 | 19.3 | 19.3 | 19.3 | 19.3 | 19.3 | 19.3 | 19.3 | 19.3 | 19.3 | 19.3 | 19.3 | 19.3 | 19.3 | 19.3 | 19.3 | 19.3 | 19.3 | 19.3 | 19.3 | 19.3 | 19.3 | 19.3 | 19.3 | 19.3 | 19.3 | 19.3 | 19.3 | 19.3 | 19.3 | 20.3 | 20.3 | 20.3 | 20.3 | 20.3 | 20.3 | 20.3 | 20.3 | 20.3 | 20.3 | 20.3 | 20.3 | 20.3 | 20.3 | 20.3 | 20.3 | 20.3 | 20.3 | 20.3 | 20.3 | 20.3 | 20.3 | 20.3 | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | 9.2 | 7.2 | 7.2 | 7.2 | 7.2 | 4.2 | 4.2 | 4.2 | 4.2 | 4.2 | 4.2 | 4.2 | 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 8.7 | 8.7 | 8.7 | 8.7 | 8.7 | 8.7 | 8.7 | 8.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 13.7 | 13.7 | 14.7 | 14.7 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 18.3 | 18.3 | 18.3 | 18.3 | 18.3 | 18.3 | 18.3 | 18.3 | 18.3 | 18.3 | 18.3 | 18.3 | 18.3 | 18.3 | 18.3 | 18.3 | 18.3 | 18.3 | 18.3 | 18.3 | 18.3 | 18.3 | 18.3 | 11.8 | 11.8 | 11.8 | 11.8 | 11.8 | 11.8 | 11.8 | 11.8 | 11.8 | 11.8 | 11.8 | 11.8 | 11.8 | 11.8 | 11.8 | 11.8 | 11.8 | 11.8 | 11.8 | 11.8 | 11.8 | 11.8 | 11.8 | 11.8 | 11.8 | 11.8 | 11.8 | 11.8 | 11.8 | 11.8 | 11.8 | 11.8 | 11.8 | 8.2 | 6.2 | 6.2 | 6.2 | 6.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 9.3 | 9.3 | 9.3 | 9.3 | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | 12.3 | 12.3 | 12.3 | 12.3 | 12.3 | 12.3 | 12.3 | 12.3 | 12.3 | 12.3 | 12.3 | 12.3 | 12.3 | 12.3 | 12.3 | 12.3 | 12.3 | 12.3 | 12.3 | 12.3 | 12.3 | 12.3 | 12.3 | 8.4 | 8.4 | 8.4 | 8.4 | 8.4 | 8.4 | 8.4 | 8.4 | 8.4 | 8.4 | 8.4 | 8.4 | 8.4 | 8.4 | 8.4 | 8.4 | 8.4 | 8.4 | 8.4 | 8.4 | 8.4 | 8.4 | 8.4 | 8.4 | 8.4 | 8.4 | 8.4 | 8.4 | 8.4 | 8.4 | 8.4 | 8.4 | 8.4 | 5 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Staff | 4: 8.7; 9: 8.5; 13: 7.7; 17: 7.7; 22: 7.7; 26: 10.7; 30: 16; 35: 17.3; 39: 17.3; 43: 17.3; 48: 17.3; 52: 17.3; 56: 17.3; 61: 17.3; 65: 17.3; 69: 17.3; 74: 17.3; 78: 18.3; 82: 18.3; 87: 18.3; 91: 18.3; 95: 18.3; 100: 14.4; 104: 11.8; 108: 11.8; 113: 11.8; 117: 11.8; 121: 11.8; 126: 11.8; 130: 11.8; 134: 6.7; 139: 3.8; 143: 3.2
| Supervising Staff | 4: 3.3; 9: 3.3; 13: 3.3; 17: 3.3; 22: 3.3; 26: 7.8; 30: 10.8; 35: 11.3; 39: 11.3; 43: 11.3; 48: 11.3; 52: 11.3; 56: 11.3; 61: 11.3; 65: 11.3; 69: 11.3; 74: 11.5; 78: 12.3; 82: 12.3; 87: 12.3; 91: 12.3; 95: 12.3; 100: 9.18; 104: 8.4; 108: 8.4; 113: 8.4; 117: 8.4; 121: 8.4; 126: 8.4; 130: 7.55; 134: 3; 139: 0; 143: 0
Month | Movements (2-way) | 1: Staff; 2: Supervising
LGV / Car | bar: 1 to 2
2019-10-01 | 386 | 1: 8.7; 2: 3.3
2019-11-01 | 382 | 1: 8.5; 2: 3.3
2019-12-01 | 366 | 1: 7.7; 2: 3.3
2020-01-01 | 366 | 1: 7.7; 2: 3.3
2020-02-01 | 366 | 1: 7.7; 2: 3.3
2020-03-01 | 606 | 1: 10.7; 2: 7.8
2020-04-01 | 832 | 1: 16; 2: 10.8
2020-05-01 | 878 | 1: 17.3; 2: 11.3
2020-06-01 | 878 | 1: 17.3; 2: 11.3
2020-07-01 | 878 | 1: 17.3; 2: 11.3
2020-08-01 | 878 | 1: 17.3; 2: 11.3
2020-09-01 | 878 | 1: 17.3; 2: 11.3
2020-10-01 | 878 | 1: 17.3; 2: 11.3
2020-11-01 | 878 | 1: 17.3; 2: 11.3
2020-12-01 | 878 | 1: 17.3; 2: 11.3
2021-01-01 | 878 | 1: 17.3; 2: 11.3
2021-02-01 | 886 | 1: 17.3; 2: 11.5
2021-03-01 | 938 | 1: 18.3; 2: 12.3
2021-04-01 | 938 | 1: 18.3; 2: 12.3
2021-05-01 | 938 | 1: 18.3; 2: 12.3
2021-06-01 | 938 | 1: 18.3; 2: 12.3
2021-07-01 | 938 | 1: 18.3; 2: 12.3
2021-08-01 | 735.2 | 1: 14.4; 2: 9.18
2021-09-01 | 652 | 1: 11.8; 2: 8.4
2021-10-01 | 652 | 1: 11.8; 2: 8.4
2021-11-01 | 652 | 1: 11.8; 2: 8.4
2021-12-01 | 652 | 1: 11.8; 2: 8.4
2022-01-01 | 652 | 1: 11.8; 2: 8.4
2022-02-01 | 652 | 1: 11.8; 2: 8.4
2022-03-01 | 618 | 1: 11.8; 2: 7.55
2022-04-01 | 334 | 1: 6.7; 2: 3
2022-05-01 | 156 | 1: 3.8; 2: 0
2022-06-01 | 144 | 1: 3.2; 2: 0
11 - General Traffic to / from Site
Includes 4 nr from NG / day

## Site Accom
HGV | Cabin Deliveries |  | Cabin Collections
| Date | Nr | Date | Nr
Temporary Set-up Surveys | 2020-03-16 | 1 | 2020-05-06 | 1 | 1 - Mobilisation | 10 - Demobilisation
Main Compound | 2020-08-25 | 24 | 2022-01-19 | 24 | 1 - Mobilisation | 10 - Demobilisation
Wogden Foot | 2021-02-18 | 2 | 2022-03-02 | 2 | 1 - Mobilisation | 10 - Demobilisation
Dunford SEC | 2021-03-24 | 4 | 2022-01-25 | 4 | 1 - Mobilisation | 10 - Demobilisation
HGV | Plant Deliveries |  | Plant Collections
| Date | Nr | Date | Nr
Temporary Set-up Surveys |  | 0 |  | 0
Main Compound | 2020-04-13 | 11 | 2021-12-20 | 11 | 1 - Mobilisation | 10 - Demobilisation
Wogden Foot | 2020-04-20 | 5 | 2022-04-04 | 5 | 1 - Mobilisation | 10 - Demobilisation
Dunford SEC | 2021-03-24 | 5 | 2022-01-25 | 5 | 1 - Mobilisation | 10 - Demobilisation
HGV | Skip Collections
| Nr | Start Date | End Date | Nr / mth
Temporary Set-up Surveys | 0
Main Compound | 89 | 2020-08-25 | 2022-01-19 | 4 | 11 - General Traffic to / from Site
Wogden Foot | 0
Dunford SEC | 0
LGV | Connections |  | Removals
| Date | Nr | Date | Nr
Temporary Set-up Surveys |  | 0 |  | 0
Main Compound | 2020-08-25 | 3 | 2022-01-19 | 3 | 1 - Mobilisation | 10 - Demobilisation
Wogden Foot |  | 0 |  | 0
Dunford SEC |  | 0 |  | 0
Note on C4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Welfare Van used for Survey work

## Operatives
Activity | Resource Nrs | Duration (days) | Total Resource days | Journeys to Site | Mob in Site | Support |  | Plant |  |  | Crane | Total |  |  | Dates
|  |  |  | Car | LGV | Moves / day | HGV | HGV | HGV (extras) | Total | HGV | Car / LGV | HGV |  | Start | Finish
Cable Installation | 9 | 24 | 216 | 216 | 72 | 0 | 0 | 4 | 2 | 12 | 0 | 288 | 12 | 7 Cable Installation | 2021-06-28 | 2021-07-20
Trough Gang 1 | 7 | 44 | 308 | 308 | 88 | see CIT | see CIT | see below | see below | see below | 0 | 396 | 0 | 7 Cable Installation | 2020-11-02 | 2021-01-12
Trench Gang 1 | 10 | 34 | 340 | 340 | 102 | see CIT | see CIT | 6 | 1 | 14 | 0 | 442 | 14 | 7 Cable Installation | 2020-12-17 | 2021-03-19
Trench Gang 2 | 10 | 34 | 340 | 340 | 102 | see CIT | see CIT | see below | see below | see below | 0 | 442 | 0 | 7 Cable Installation | 2020-12-17 | 2021-03-19
Joint Bays | 10 | 24 | 240 | 240 | 72 | see CIT | see CIT | see below | see below | see below | 0 | 312 | 0 | 7 Cable Installation | 2021-06-09 | 2021-08-13
Tunnel Steelwork Team | 5 | 34 | 170 | 170 | 68 | 0 | 0 | 2 | 0 | 4 | 0 | 238 | 4 | 7 Cable Installation | 2021-01-13 | 2021-07-01
Access Works BUE
Mobilisation / Induction | 14 | 18 | 252 | 252 | 72 | see CIT | see CIT | 3 | 2 | 5 | 0 | 324 | 5 | 2 Enabling Works | 2020-04-17 | 2020-04-17
1. Haul Road | 7 | 60 | 420 | 420 | 120 | see CIT | see CIT | see above | see above | see above | 0 | 540 | 0 | 3 Access Road | 2021-02-12 | 2021-02-22
2. Temporary TPT | 14 | 60 | 840 | 840 | 240 | see CIT | see CIT | see above | see above | see above | 0 | 1080 | 0 | 4 TPT | 2020-08-24 | 2020-11-02
[Bridge Team] | 14 | 25 | 350 | 350 | 100 | see CIT | see CIT | see above | see above | see above | 2 | 450 | 2 | 5 Permanent Bridge | 2020-09-16 | 2020-10-13
| 14 | 30 | 420 | 420 | 120 | see CIT | see CIT | see above | see above | see above | 0 | 540 | 0 | 6 Temporary Bridge | 2020-04-17 | 2020-10-22
[Culvert Team] | 14 | 35 | 490 | 490 | 140 | see CIT | see CIT | see above | see above | see above | 0 | 630 | 0 | 2 Enabling Works | 2020-12-01 | 2021-02-24
8. Tower Removal Access | 14 | 10 | 140 | 140 | 40 | see CIT | see CIT | see above | see above | see above | 0 | 180 | 0 | 2 Enabling Works | 2021-07-19 | 2021-08-27
10. Reinstatement - Tower Access | 14 | 25 | 350 | 350 | 100 | see CIT | see CIT | see above | see above | see above | 0 | 450 | 0 | 10 Reinstatement | 2022-01-17 | 2022-02-02
11. Reinstatement - TPT | 14 | 50 | 700 | 700 | 200 | see CIT | see CIT | see above | see above | see above | 0 | 900 | 0 | 10 Reinstatement | 2021-12-07 | 2022-02-22
12. Reinstatement - Haul Road | 14 | 30 | 420 | 420 | 120 | see CIT | see CIT | see above | see above | see above | 0 | 540 | 0 | 10 Reinstatement | 2022-01-27 | 2022-03-17
13. Site Compounds | 14 | 5 | 70 | 70 | 20 | see CIT | see CIT | see above | see above | see above | 0 | 90 | 0 | 6 Temporary Bridge | 2020-09-15 | 2020-09-16
| 14 | 10 | 140 | 140 | 40 | see CIT | see CIT | see above | see above | see above | 0 | 180 | 0 | 8 Construction of SEC | 2020-12-01 | 2021-08-24
De-mobilisation | 14 | 18 | 252 | 252 | 72 | see CIT | see CIT | 3 | 2 | 5 | 0 | 324 | 5 | 10 Reinstatement | 2022-03-17 | 2022-03-17
OHL Works
Wiring Install | 20 | 70 | 1400 | 1400 | 350 | 8 | 560 | 13 | 2 | 30 | 3 | 1750 | 593 | 9 Removal of OHL | 2021-03-30 | 2021-11-01
Gantry Erection | 6 | 10 | 60 | 60 | 20 | 8 | 0 | 2 | 0 | 4 | 2 | 80 | 6 | 9 Removal of OHL | 2021-03-12 | 2021-04-09
Dismantle Towers & Cutting Up | 8 | 15 | 120 | 120 | 30 | 8 | 0 | 0 | 0 | 0 | 8 | 150 | 8 | 9 Removal of OHL | 2021-11-02 | 2021-12-03
Tower Foundations | 6 | 15 | 90 | 90 | 30 | 8 | 120 | 4 | 2 | 12 | 0 | 120 | 132 | 9 Removal of OHL | 2021-03-08 | 2021-03-29
|  |  |  | 8128 | 2318 |  | 680 |  |  | 86 | 15 | 10446 | 781
Mob in Site
Operatives / crew vehicle |  |  |  |  | 4
Formulas:
Finish = [Finish, row below]
Finish = [Dates]
Dates = [Dates, row above]
Dates = MIN([Dates, row below]:V25)

## Materials
Tenderer name: | Morgan Sindall (BakerHicks)
Final Design / As built |  |  | Use this sheet to calculate the impact the final or as built design by selecting the number of each item required from the list below.
Assumptions, exclusions, substitutions and omission:- Also record any changes in scope, or any complimentary projects
Item |  |  |  |  | Reason |  |  |  | Expected Significance
Removal of existing towers and conductors - omitted
CBS Substituted for CEM I in Direct Buried section |  |  |  |  | No CBS Section
|  |  | Summary Results by type of emissions | [7 empty] | Area |  |  | HGV Loads | LGV Loads
PAS code |  | Total | Materials | Transport | Plant | SF6 |  |  |  |  | Construction of SEC |  |  | 73.1667 | 6
tCO2 |  |  | A1-3 | A4 | A5 | B1 |  |  |  |  | Enabling works |  |  | 19.9167 | 1
Carbon added |  | 3635.641 | 3238.4973 | 376.9047 | 20.2389 | 0 |  |  |  |  | Access Road |  |  | 340.125 | 0
Carbon avoided |  | 25.8742 | 25.8408 | 0.033388 | 0 | 0 |  |  |  |  | Trans Pennine Trail Diversion |  |  | 540 | 0
[11 empty] | Permanent Bridge |  |  | 10.3375 | 0
Item List | [10 empty] | Temporary Bridge |  |  | 41.5 | 0 | [20 empty] | Added |  |  |  |  | Avoided
[11 empty] | Removal of OHL |  |  | 99.515 | 4
[11 empty] | Cable Installation |  |  | 1857.0677 | 4
[11 empty] | Reinstatement & Demobilisation |  |  | 925.6667 | 0
M&E Assets | [14 empty] | m3/load | [7 empty] | A1-3 | A1-3 |  |  | A4 | A5 | B1 | B6 | [5 empty] | Materials | Transport | Plant | SF6 | End of Life | Materials | Transport | Plant | SF6 | End of Life
[15 empty] | 8 | [7 empty] | Component | Component | [11 empty] | A1-3 | A4 | A5 | B1 | C1-4 | A1-3 | A4 | A5 | B1 | C1-4
[15 empty] | Install |  |  | Remove
AIS Equipment Only - Does not include structures or foundations | [6 empty] | Origin | Transport Distance |  | End of Life | Comments | kgCO2 Added | kgCO2 Avoided | Area | HGV Loads |  | LGV Loads | HGV Loads | LGV Loads | Comment |  |  | kgCO2e | kgCO2e | Distance | Mode | Transport Op | Plant |  |  | Waste Process | Disposal
Voltage | Equipment |  |  |  | Quantity | Units | Option | Option | km | Option | [5 empty] | Mobilisation |  |  |  |  | Item ref | Mass | Manufacture | Civil | kgkm | type | kgCO2 | kgCO2 |  |  | kgCO2 | kgCO2 | Total | Emissions added | Emissions avoided
400kV | Gantry, Single Circuit |  |  |  | 2 | n | New | Default |  | --Disposal M&E-- | Gantry | 92158.7031 | 0 | Construction of SEC | 6 | Enabling works |  |  |  | 3 movements per gantry | SUB01001 | 171504 | 86889.8 | 0 | 41160960 | Road | 5158.7031 | 110.2 |  |  | 4.2989 | 0 | 92158.7031 | 92158.7031 | 0 | 86889.8 | 5158.7031 | 110.2 |  |  | 0 | 0 | 0
400kV | Cable Sealing End Porcelain 1ph |  |  |  | 6 | n | New | Default |  | --Disposal M&E-- | CSE | 43517.4879 | 0 | Construction of SEC | 6 | Access Road |  |  |  | One movement per piece of equipment | SUB01014 | 6178 | 42960 | 0 | 4448160 | Road | 557.4879 | 0 |  |  | 0.46457 | 0 | 43517.4879 | 43517.4879 | 0 | 42960 | 557.4879 | 0 |  |  | 0 | 0 | 0
400kV | Earth Switch 3ph |  |  |  | 6 | n | New | Default |  | --Disposal M&E-- | ES | 69173.9781 | 0 | Construction of SEC | 6 | Trans Pennine Trail Diversion |  |  |  | One movement per piece of equipment | SUB01087 | 1928 | 69000 | 0 | 1388160 | Road | 173.9781 | 0 |  |  | 0.14498 | 0 | 69173.9781 | 69173.9781 | 0 | 69000 | 173.9781 | 0 |  |  | 0 | 0 | 0
400kV | Porcelain SA 1ph |  |  |  | 6 | n | New | Default |  | --Disposal M&E-- | SA | 3968.2607 | 0 | Construction of SEC | 6 | Permanent Bridge |  |  |  | One movement per piece of equipment | SUB01006 | 424 | 3930 | 0 | 305280 | Road | 38.2607 | 0 |  |  | 0.031884 | 0 | 3968.2607 | 3968.2607 | 0 | 3930 | 38.2607 | 0 |  |  | 0 | 0 | 0
400kV | CT 1ph |  |  |  | 6 | n | New | Default |  | --Disposal M&E-- | CT | 13414.7495 | 0 | Construction of SEC | 6 | Temporary Bridge |  |  |  | One movement per piece of equipment | SUB01010 | 1050 | 13320 | 0 | 756000 | Road | 94.7495 | 0 |  |  | 0.078958 | 0 | 13414.7495 | 13414.7495 | 0 | 13320 | 94.7495 | 0 |  |  | 0 | 0 | 0
--Equipment Voltage-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 |  | Cable Installation |  |  |  |  | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Equipment Voltage-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 |  | Construction of SEC |  |  |  |  | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Equipment Voltage-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 |  | Removal of OHL |  |  |  |  | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Equipment Voltage-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 |  | Reinstatement & Demobilisation |  |  |  |  | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Equipment Voltage-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 |  | General Traffic to / from Site |  |  |  |  | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Equipment Voltage-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Equipment Voltage-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Equipment Voltage-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Equipment Voltage-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Equipment Voltage-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Equipment Voltage-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Equipment Voltage-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Equipment Voltage-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Equipment Voltage-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Equipment Voltage-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Equipment Voltage-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Equipment Voltage-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Equipment Voltage-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Equipment Voltage-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Equipment Voltage-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Equipment Voltage-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Equipment Voltage-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Equipment Voltage-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
0
SF6 Added or Removed from the Substation Design - calculation includes the production of SF6 and UK average leakage rates over a 30y life of the asset | [10 empty] | Comments | kgCO2 Added | kgCO2 Avoided | 0
[5 empty] | Quantity | Units | Leak rate / yr | [6 empty] | 0
SF6 Added to the Substation | [5 empty] | kg | [5 empty] | 0 | 0 | 0 | [6 empty] | SUB1010 | 0 | [6 empty] | 0 |  |  |  |  | 0
SF6 Removed from the design by layout or kit selection | [5 empty] | kg | [5 empty] | 0 | 0 | 0 | [6 empty] | SUB1010 | 0 | [6 empty] | 0 | [5 empty] | 0
0
Steelwork - Support Structure | [6 empty] | Origin | Transport Distance |  | End of Life | Comments | kgCO2 Added | kgCO2 Avoided | 0
Total weight of steel required |  |  |  |  | Quantity | Units | Option | Option | km | Option |  |  |  | 0
Galvanised steel |  |  |  |  | 2.5 | t | Reused from onsite | Default |  | --Disposal M&E-- | ES Support | 0 | 7284.3997 | Construction of SEC | 2 |  |  |  |  | Two movements per structure | SUB10001 | 1000 | 7275 | 0 | 75000 | Road | 9.3997 | 0 |  |  | 0.031332 | 0 | 7284.3997 | 0 | 7284.3997 | 0 | 0 | 0 |  |  | 7275 | 9.3997 | 0
Galvanised steel |  |  |  |  | 1.34 | t | Reused from onsite | Default |  | --Disposal M&E-- | SA Support | 0 | 3904.4383 | Construction of SEC | 2 |  |  |  |  | Two movements per structure | SUB10001 | 1000 | 3899.4 | 0 | 40200 | Road | 5.0383 | 0 |  |  | 0.016794 | 0 | 3904.4383 | 0 | 3904.4383 | 0 | 0 | 0 |  |  | 3899.4 | 5.0383 | 0
Galvanised steel |  |  |  |  | 3.7 | t | Reused from onsite | Default |  | --Disposal M&E-- | CSE Support | 0 | 10780.9116 | Construction of SEC | 2 |  |  |  |  | Two movements per structure | SUB10001 | 1000 | 10767 | 0 | 111000 | Road | 13.9116 | 0 |  |  | 0.046372 | 0 | 10780.9116 | 0 | 10780.9116 | 0 | 0 | 0 |  |  | 10767 | 13.9116 | 0
Galvanised steel |  |  |  |  | 1.34 | t | Reused from onsite | Default |  | --Disposal M&E-- | CT Support | 0 | 3904.4383 | Construction of SEC | 2 |  |  |  |  | Two movements per structure | SUB10001 | 1000 | 3899.4 | 0 | 40200 | Road | 5.0383 | 0 |  |  | 0.016794 | 0 | 3904.4383 | 0 | 3904.4383 | 0 | 0 | 0 |  |  | 3899.4 | 5.0383 | 0
Galvanised steel | [5 empty] | t | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB10001 | 1000 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Concrete Supports | [13 empty] | 0 | [21 empty] | 0 | 0 | 0
Steel Reinforcement (rebar) | [5 empty] | t | New | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB20697 | 1000 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Standard Strength Concrete Mixes-- | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB20121 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Standard Strength Concrete Mixes-- | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB20121 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Standard Strength Concrete Mixes-- | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB20121 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
0
GIS Indoor Bays - industry average of bay design, no SF6, no foundations | [6 empty] | Origin | Transport Distance |  | End of Life | Comments | kgCO2 Added | kgCO2 Avoided | 0
Component |  |  |  |  | Quantity | Units | Option | Option | km | Option |  |  |  | 0
--GIS Indoor Bays-- | [5 empty] | n | New | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--GIS Indoor Bays-- | [5 empty] | n | New | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--GIS Indoor Bays-- | [5 empty] | n | New | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--GIS Indoor Bays-- | [5 empty] | n | New | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--GIS Indoor Bays-- | [5 empty] | n | New | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
GIS Bushings Equipment | [5 empty] | n | New | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00241 | 908.5 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
and Foundation | [5 empty] | n | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00242 | 6721 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[14 empty] | 0 | [6 empty] | SUB00000
Conductors - presented as single lengths and not as circuits - please make sure you include the complete length | [6 empty] | Origin | Transport Distance |  | End of Life | Comments | kgCO2 Added | kgCO2 Avoided | 0 | [6 empty] | SUB00000
Component |  | Type | mm2 |  | Quantity | Units | Option | Mode | km | Option |  |  |  | 0 | [6 empty] | 0
Araucaria (per km) |  | " " | " " |  | 10.055 | km | New | Default |  | --Disposal M&E-- |  | 136769.9551 | 0 | Removal of OHL |  |  |  | 10 |  | All OHL materials under Removal of OHL section | OHL01407 | 2412 | 136162.0379 | 0 | 4850532 | Road | 607.9172 | 0 |  |  | 0.30396 | 0 | 136769.9551 | 136769.9551 | 0 | 136162.0379 | 607.9172 | 0 |  |  | 0 | 0 | 0
--Conductors-- |  | " " | " " |  |  | km | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | OHL10000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Conductors-- |  | " " | " " |  |  | km | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | OHL10000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Conductors-- |  | " " | " " |  |  | km | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | OHL10000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Conductors-- |  | " " | " " |  |  | km | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | OHL10000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Conductors-- |  | " " | " " |  |  | km | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | OHL10000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Conductors-- |  | " " | " " |  |  | km | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | OHL10000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Conductors-- |  | " " | " " |  |  | km | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | OHL10000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Conductors-- |  | " " | " " |  |  | km | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | OHL10000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Conductors-- |  | " " | " " |  |  | km | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | OHL10000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Conductors-- |  | " " | " " |  |  | km | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | OHL10000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Conductors-- |  | " " | " " |  |  | km | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | OHL10000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[14 empty] | 0 | [6 empty] | SUB00000
Tension and Suspension Sets | [6 empty] | Origin | Transport Distance |  | End of Life | Comments | kgCO2 Added | kgCO2 Avoided | 0 | [6 empty] | 0
Insulator Type - Bundle - Tower Type - Rating (kV) - Conductor Type |  |  |  |  | Quantity | Units | Option | Mode | km | Option |  |  |  | 0 | [6 empty] | SUB00000
300kN Glass Tension Dish |  |  |  |  | 12 | n | New | Default |  | --Disposal M&E-- | 6 Tension Sets | 164.9843 | 0 | Removal of OHL |  |  |  |  | 2 |  | OHL01513 | 11.1 | 161.6455 | 0 | 26640 | Road | 3.3388 | 0 |  |  | 0.0016694 | 0 | 164.9843 | 164.9843 | 0 | 161.6455 | 3.3388 | 0 |  |  | 0 | 0 | 0
300kN Glass Suspension Dish |  |  |  |  | 6 | n | New | Default |  | --Disposal M&E-- | 6 Suspention Sets | 82.4921 | 0 | Removal of OHL |  |  |  |  | 2 |  | OHL01512 | 11.1 | 80.8227 | 0 | 13320 | Road | 1.6694 | 0 |  |  | 0.0008347 | 0 | 82.4921 | 82.4921 | 0 | 80.8227 | 1.6694 | 0 |  |  | 0 | 0 | 0
--Tension set-- | [5 empty] | km | New | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | OHL10000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Tension set-- | [5 empty] | km | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | OHL10000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Tension set-- | [5 empty] | km | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | OHL10000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Tension set-- | [5 empty] | km | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | OHL10000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Tension set-- | [5 empty] | km | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | OHL10000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Tension set-- | [5 empty] | km | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | OHL10000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Tension set-- | [5 empty] | km | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | OHL10000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[14 empty] | 0 | [6 empty] | SUB00000
Towers | [6 empty] | Origin | Transport Distance |  | End of Life | Comments | kgCO2 Added | kgCO2 Avoided | 0 | [6 empty] | SUB00000
Component |  |  |  |  | Quantity | Units | Option | Mode | km | Option |  |  |  | 0 | [6 empty] | 0
Tower Steelwork & Bolts | [13 empty] | 0 | [6 empty] | SUB00000
Replacement Tower Steelwork | [5 empty] | t | New | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | OHL00602 | 1000 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Bolts / stepbolts / nuts | [5 empty] | t | New | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | OHL00600 | 1000 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Complete Towers |  |  |  |  | Quantity | Units | Option | Mode | km | Option |  |  |  | Removal of OHL |  |  |  | 20 |  | Guesstimate | SUB00000
L12-D25 E6 |  |  |  |  | 1 | n | New | Default |  | --Disposal M&E-- |  | 107214.7903 | 0 | 0 | [6 empty] | OHL00102 | 34745 | 106779.3313 | 0 | 3474500 | Road | 435.4591 | 0 |  |  | 0.43546 | 0 | 107214.7903 | 107214.7903 | 0 | 106779.3313 | 435.4591 | 0 |  |  | 0 | 0 | 0
--Towers-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | OHL10002 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Towers-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | OHL10002 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Towers-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | OHL10002 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Towers-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | OHL10002 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Towers-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | OHL10002 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Towers-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | OHL10002 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Towers-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | OHL10002 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Towers-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | OHL10002 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Towers-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | OHL10002 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Towers-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | OHL10002 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Towers-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | OHL10002 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Towers-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | OHL10002 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Towers-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | OHL10002 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Towers-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | OHL10002 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[14 empty] | 0 | [6 empty] | SUB00000
Cables | [6 empty] | Origin | Transport Distance |  | End of Life | Comments | kgCO2 Added | kgCO2 Avoided | 0 | [6 empty] | 0
Component |  |  |  |  | Quantity | Units | Option | Option | km | Option |  |  |  | 0 | [6 empty] | 0
400kV cable 2500mm2 |  |  |  |  | 11856 | m | New | France | 1000 | --Disposal M&E-- |  | 1620148.5955 | 0 | Cable Installation | 24 |  |  |  |  | Drum deliveries and collections | SUB12500 | 37.2 | 1576848 | 0 | 0 | FALSE | 43300.5955 | 0 |  |  | 5.5276 | 0 | 1620148.5955 | 1620148.5955 | 0 | 1576848 | 43300.5955 | 0 |  |  | 0 | 0 | 0
--Cables-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Cables-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Cables-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Cables-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Cables-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Cables-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Cables-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Cables-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Cables-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Cables-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Cables-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Cables-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[14 empty] | 0 | [6 empty] | SUB00000
Transformers - No support structures or foundations | [6 empty] | Origin | Transport Distance |  | End of Life | Comments | kgCO2 Added | kgCO2 Avoided | 0 | [6 empty] | SUB00000
Component |  |  |  |  | Quantity | Units | Option | Option | km | Option |  |  |  | 0 | [6 empty] | 0
1100MVA Interbus- 400/275kV | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00254 | 227800 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
240MVA SGT 400/132kV | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00259 | 188400 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
180MVA SGT 400/132kV | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00264 | 80000 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
240MVA SGT 275/132kV | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00269 | 148700 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[14 empty] | 0 | [5 empty] | Consider 3 empties - could be 6 extra deliveries | SUB00000 | 0
Busbars | [6 empty] | Origin | Transport Distance |  | End of Life | Comments | kgCO2 Added | kgCO2 Avoided | 0 | [6 empty] | SUB00000 | 0
Component |  |  |  |  | Quantity | Units | Option | Option | km | Option |  |  |  | 0 | [6 empty] | 0 | 0
AIS 140mm Diameter Single Phase |  |  |  |  | 60 | m | New | Road |  | Recycled/Reuse |  | 6085.7143 | 0 | Construction of SEC | 3 | [5 empty] | SUB00280 | 11 | 6085.7143 | 0 | 0 | Road | 0 | 0 |  |  | 0.0082718 | 0 | 6085.7143 | 6085.7143 | 0 | 6085.7143 | 0 | 0 |  |  | 0 | 0 | 0
--Busbars-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Busbars-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Busbars-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Busbars-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Busbars-- | [5 empty] | n | --Source-- | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[14 empty] | 0 | [6 empty] | SUB00000
Control Rooms - industry average design based on previous projects | [6 empty] | Origin | Transport Distance |  | End of Life | Comments | kgCO2 Added | kgCO2 Avoided | 0 | [6 empty] | SUB00000
Component |  | Type |  |  | Quantity | Units | Option | Option | km | Option |  |  |  | 0 | [6 empty] | 0
Amenity Module |  | Equipment & |  |  |  | n | New | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB10302 | 74773 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
|  | Foundation |  |  |  | n | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Battery Room Module |  | Equipment & |  |  |  | n | New | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB10304 | 21870.48 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
|  | Foundation |  |  |  | n | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Control Permit Room |  | Building & |  |  |  | n | New | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
|  | Foundation |  |  |  | n | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
LVAC Module |  | Building & |  |  |  | n | New | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB10308 | 26610.84 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
|  | Foundation |  |  |  | n | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
|  | Board |  |  |  | n | New | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Portable Relay Room |  | Building & |  |  |  | n | New | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB10311 | 20692.899 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
|  | Foundation |  |  |  | n | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Protection Room |  | Building & |  |  |  | n | New | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB10313 | 26330.74 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
|  | Foundation |  |  |  | n | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Telecom Room |  | Building & |  |  |  | n | New | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB10315 | 26330 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
|  | Foundation |  |  |  | n | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Diesel generator |  | Equipment |  |  |  | n | New | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Diesel generator |  | Equipment & |  |  |  | n | New | Default |  | --Disposal M&E-- |  | 0 | 0 | 0 | [6 empty] | SUB10317 | 207000 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
|  | Foundation |  |  |  |  | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | n | [6 empty] | 0 | [6 empty] | SUB00000 | [12 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Civil Assets | [6 empty] | n | [6 empty] | 0 | [6 empty] | SUB00000
[14 empty] | 0 | [6 empty] | SUB00000
Demolition | [6 empty] | Origin | Transport Distance |  | End of Life | Comments | kgCO2 Added | kgCO2 Avoided | 0 | [6 empty] | SUB00000
Component |  |  |  |  | Quantity | Units | Option | Option | km | Option |  |  |  | 0 | [6 empty] | 0
Concrete bases - removal and backfill with Type 1 |  |  |  |  | 85 | m3 | New | Road |  | Recycled/Reuse | Removal of concrete foundations down 1.1 Dunbridge Cmpund | 1338.495 | 0 | Reinstatement & Demobilisation |  |  |  | 10.625 |  | Dunford Bridge demolition considered 'Reinstatement' | SUB10380 | 2800 | 0 | 1249.5 | 0 | Road | 0 | 88.995 |  |  | 2.9829 | 0 | 1338.495 | 1338.495 | 0 | 1249.5 | 0 | 88.995 |  |  | 0 | 0 | 0
Remove existing palisade fence |  |  |  |  | 200 | m | New | Road |  | --Disposal Civil-- | Removal of fence for Dunbridge Compound | 212.4006 | 0 | Reinstatement & Demobilisation |  |  |  | 16.6667 |  | 12m of fencing per load (3m width, four deep stacked) | SUB00528 | 361 | 0 | 106.2006 | 0 | Road | 0 | 106.2 |  |  | 0.27146 | 0 | 212.4006 | 212.4006 | 0 | 106.2006 | 0 | 106.2 |  |  | 0 | 0 | 0
Existing stone | [5 empty] | m3 | [7 empty] | Reinstatement & Demobilisation |  |  |  | 0
Cable trenches - removal to 150mm including backfill Type 1 |  |  |  |  | 130 | m3 | New | Road |  | --Disposal Civil-- |  | 87.2599 | 0 | Reinstatement & Demobilisation |  |  |  | 16.25 |  | Dunford Bridge demolition considered 'Reinstatement' | SUB10381 | 1152 | 0 | 0.1599 | 0 | Road | 0 | 87.1 |  |  | 0.56308 | 0 | 87.2599 | 87.2599 | 0 | 0.1599 | 0 | 87.1 |  |  | 0 | 0 | 0
--Demolition-- | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB000012 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Demolition-- | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB000012 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Demolition-- | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB000012 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Demolition-- | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB000012 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[14 empty] | 0 | [6 empty] | SUB00000
Earthworks | [6 empty] | Origin | Transport Distance |  | End of Life | Comments | kgCO2 Added | kgCO2 Avoided | 0 | [6 empty] | SUB00000
Component |  | Type |  |  | Quantity | Units | Option | Option | km | Option |  |  |  | 0 | [6 empty] | 0
Excavation |  |  |  |  | 765 | m3 | New | Default |  | Landfill | Cut and fill Wogden Foot | 6268.2647 | 0 | Construction of SEC | 0 |  |  |  |  | Not moved off site | SUB00374 | 1900 | 0 | 0 | 43605000 | Road | 5465.0147 | 803.25 |  |  | 5.465 | 0 | 6268.2647 | 6268.2647 | 0 | 0 | 5465.0147 | 803.25 |  |  | 0 | 0 | 0
Terram 1000 geotextile membrane |  |  |  |  | 20000 | m2 | New | Default |  | --Disposal Civil-- | Membrane under Haul road and surround of Duct trench | 38852.1122 | 0 | Access Road | 5 |  |  | 5 |  |  | SUB10411 | 0.693 | 0 | 38800 | 415800 | Road | 52.1122 | 0 |  |  | 0.052112 | 0 | 38852.1122 | 38852.1122 | 0 | 38800 | 52.1122 | 0 |  |  | 0 | 0 | 0
Strip Topsoil |  |  |  |  | 1800 | m3 | New | Default |  | --Disposal Civil-- | Strip top soil from TPT and Haul road | 14802.831 | 0 | Trans Pennine Trail Diversion | 0 |  |  |  |  | Not moved off site | SUB00392 | 2050 | 0 | 0 | 110700000 | Road | 13874.031 | 928.8 |  |  | 13.874 | 0 | 14802.831 | 14802.831 | 0 | 0 | 13874.031 | 928.8 |  |  | 0 | 0 | 0
Strip Topsoil |  |  |  |  | 1750 | m3 | New | Default |  | --Disposal Civil-- | Strip top soil from TPT Diversion | 14391.6412 | 0 | Trans Pennine Trail Diversion | 0 |  |  |  |  | Not moved off site | SUB00392 | 2050 | 0 | 0 | 107625000 | Road | 13488.6412 | 903 |  |  | 13.4886 | 0 | 14391.6412 | 14391.6412 | 0 | 0 | 13488.6412 | 903 |  |  | 0 | 0 | 0
--Earthworks-- | [5 empty] | n | --Source-- | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Earthworks-- | [5 empty] | n | --Source-- | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Earthworks-- | [5 empty] | n | --Source-- | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[14 empty] | 0 | [6 empty] | SUB00000
Piling - based on some standard items | [6 empty] | Origin | Transport Distance |  | End of Life | Comments | kgCO2 Added | kgCO2 Avoided | 0 | [6 empty] | SUB00000
Component |  |  |  |  | Quantity | Units | Option | Option | km | Option |  |  |  | 0 | [6 empty] | 0
|  | Length (m) | Diameter (m) | No. | [9 empty] | 0 | [6 empty] | SUB00000
CFA Pile |  |  |  |  | 0 | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB25001 | 1916.3 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
CFA Pile |  |  |  |  | 0 | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB25001 | 1916.3 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
CFA Pile |  |  |  |  | 0 | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB25001 | 1916.3 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
CFA Pile |  |  |  |  | 0 | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB25001 | 1916.3 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
CFA Pile |  |  |  |  | 0 | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB25001 | 1916.3 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
CFA Pile |  |  |  |  | 0 | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB25001 | 1916.3 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Pile cut down | [5 empty] | m | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00430 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
| Pile Dia (m) | Helix Dia (m) | Length (m) | No. |  | n | [7 empty] | 0 | [6 empty] | SUB00000
Helical Pile |  |  |  |  | 0 | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB25002 | 7850 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Helical Pile |  |  |  |  | 0 | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB25002 | 7850 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Helical Pile |  |  |  |  | 0 | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB25002 | 7850 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Testing Prelim & Working | [5 empty] | n | --Source-- | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00429 | 1240 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Integrity testing (each pile) | [5 empty] | n | --Source-- | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00431 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Pile Caps | [5 empty] | n | [7 empty] | 0 | [6 empty] | SUB00000
Steel Reinforcement (rebar) | [5 empty] | t | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB20697 | 1000 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Standard Strength RC40/50 Cem I | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB10694 | 2380 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Standard Strength Concrete Mixes-- | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB20121 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Standard Strength Concrete Mixes-- | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB20121 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Galvanised steel | [5 empty] | t | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB10001 | 1000 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Galvanised steel | [5 empty] | t | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB10001 | 1000 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[6 empty] | n | [7 empty] | 0 | [6 empty] | SUB00000
Concrete Foundations | [6 empty] | Origin | Transport Distance |  | End of Life | Comments | kgCO2 Added | kgCO2 Avoided | 0 | [6 empty] | SUB00000
Component |  |  |  |  | Quantity | Units | Option | Option | km | Option |  |  |  | 0 | [6 empty] | 0
Steel Reinforcement (rebar) |  |  |  |  | 60 | t | New | Default |  | Landfill |  | 87825.594 | 0 | Construction of SEC | 15 |  |  |  |  | 5t per load. Add 3 part loads | SUB20697 | 1000 | 0 | 87600 | 1800000 | Road | 225.594 | 0 |  |  | 0.22559 | 0 | 87825.594 | 87825.594 | 0 | 87600 | 225.594 | 0 |  |  | 0 | 0 | 0
Standard Strength RC40/50 Cem I |  |  |  |  | 355 | m3 | New | Default |  | Recycled/Reuse | Gantry | 134171.7395 | 0 | Removal of OHL | 47.375 |  |  |  |  | Add 3 part loads | SUB10694 | 2380 | 0 | 130995 | 25347000 | Road | 3176.7395 | 0 |  |  | 10.5891 | 0 | 134171.7395 | 134171.7395 | 0 | 130995 | 3176.7395 | 0 |  |  | 0 | 0 | 0
Standard Strength RC40/50 Cem I |  |  |  |  | 84 | m3 | New | Default |  | Recycled/Reuse | Primary Foundation | 31747.6792 | 0 | Removal of OHL | 13.5 |  |  |  |  | Add 3 part loads | SUB10694 | 2380 | 0 | 30996 | 5997600 | Road | 751.6792 | 0 |  |  | 2.5056 | 0 | 31747.6792 | 31747.6792 | 0 | 30996 | 751.6792 | 0 |  |  | 0 | 0 | 0
Standard Strength RC40/50 Cem I |  |  |  |  | 45.12 | m3 | New | Default |  | Recycled/Reuse | Tower | 17053.0391 | 0 | Removal of OHL | 8.64 |  |  |  |  | Add 3 part loads | SUB10694 | 2380 | 0 | 16649.28 | 3221568 | Road | 403.7591 | 0 |  |  | 1.3459 | 0 | 17053.0391 | 17053.0391 | 0 | 16649.28 | 403.7591 | 0 |  |  | 0 | 0 | 0
Standard Strength RC40/50 Cem I |  |  |  |  | 68 | m3 | New | Default |  | Recycled/Reuse | Temporary Bridge Foundation | 25700.5022 | 0 | Temporary Bridge | 11.5 |  |  |  |  | Add 3 part loads | SUB10694 | 2380 | 0 | 25092 | 4855200 | Road | 608.5022 | 0 |  |  | 2.0283 | 0 | 25700.5022 | 25700.5022 | 0 | 25092 | 608.5022 | 0 |  |  | 0 | 0 | 0
Standard Strength RC40/50 Cem I |  |  |  |  | 26.7 | m3 | New | Default |  | Recycled/Reuse | Permanent Bridge Foundation | 10091.2266 | 0 | Permanent Bridge | 6.3375 |  |  |  |  | Add 3 part loads | SUB10694 | 2380 | 0 | 9852.3 | 1906380 | Road | 238.9266 | 0 |  |  | 0.79642 | 0 | 10091.2266 | 10091.2266 | 0 | 9852.3 | 238.9266 | 0 |  |  | 0 | 0 | 0
--Standard Strength Concrete Mixes-- | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB20121 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Standard Strength Concrete Mixes-- | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB20121 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Standard Strength Concrete Mixes-- | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB20121 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Standard Strength Concrete Mixes-- | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB20121 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Standard Strength Concrete Mixes-- | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB20121 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Standard Strength Concrete Mixes-- | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB20121 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Standard Strength Concrete Mixes-- | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB20121 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Standard Strength Concrete Mixes-- | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB20121 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Standard Strength Concrete Mixes-- | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB20121 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[14 empty] | 0 | [6 empty] | SUB00000
Scaffolding | [6 empty] | Origin | Transport Distance |  | End of Life | Comments | kgCO2 Added | kgCO2 Avoided | 0 | [6 empty] | SUB00000
|  |  | Length | Weeks | Quantity | Unit | Option | Mode | km | Option |  |  |  | 0 | [6 empty] | SUB00000
--Scaffolding-- |  |  |  |  | 0 | m | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | OHL10005 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Scaffolding-- |  |  |  |  | 0 | m | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | OHL10005 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Scaffolding-- |  |  |  |  | 0 | m | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | OHL10005 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Scaffolding-- |  |  |  |  | 0 | m | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | OHL10005 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Scaffolding-- |  |  |  |  | 0 | m | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | OHL10005 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Scaffolding-- |  |  |  |  | 0 | m | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | OHL10005 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Wire Fence |  |  |  |  | 0 | m per week | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | OHL00512 | 3 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
|  |  | m2 | Weeks | Quantity | Unit | Option | Mode | km | Option |  |  |  | 0 | [6 empty] | SUB00000 | [12 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Scaffolding netting |  |  |  |  | 0 | m2 per week | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | OHL00510 | 0.08 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
|  |  | Weight | Weeks | Quantity | Unit | Option | Mode | km | Option |  |  |  | 0 | [6 empty] | SUB00000 | [12 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Kentledge Blocks |  |  |  |  | 0 | t per week | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | OHL00509 | 1000 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
|  |  | Panels | Weeks | Quantity | Unit | Option | Mode | km | Option |  |  |  | 0 | [6 empty] | SUB00000 | [12 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Heras Type Panel Fence |  |  |  |  | 0 | m per week | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | OHL00511 | 51.4 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[14 empty] | 0 | [6 empty] | SUB00000 | [14 empty] | 0 | 0 | 0
Roadways and Hard standing | [6 empty] | Origin | Transport Distance |  | End of Life | Comments | kgCO2 Added | kgCO2 Avoided | 0 | [6 empty] | SUB00000 | [14 empty] | 0 | 0 | 0
Component |  |  |  |  | Quantity | Units | Option | Option | km | Option |  |  |  | 0 | [6 empty] | 0 | [14 empty] | 0 | 0 | 0
Road (tarmac) |  |  |  |  | 1400 | m2 | New | Default |  | --Disposal Civil-- | Haul Road from Windell Edge | 160738.1143 | 0 | Access Road | 24.5 |  |  |  |  | 140mm depth | SUB00525 | 1812 | 0 | 150827.6 | 76104000 | Road | 9538.1143 | 372.4 |  |  | 9.5381 | 0 | 160738.1143 | 160738.1143 | 0 | 150827.6 | 9538.1143 | 372.4 |  |  | 0 | 0 | 0
[14 empty] | Reinstatement & Demobilisation |  |  |  | 24.5
Crushed stone temporary access road |  |  |  |  | 1845 | m3 | New | Default |  | --Disposal Civil-- | Haul Road Windell Edge | 56667.8558 | 0 | Access Road | 230.625 | [5 empty] | SUB10519 | 7150 | 0 | 6088.5 | 395752500 | Road | 49599.6608 | 979.695 |  |  | 49.5997 | 0 | 56667.8558 | 56667.8558 | 0 | 6088.5 | 49599.6608 | 979.695 |  |  | 0 | 0 | 0
[14 empty] | Reinstatement & Demobilisation |  |  |  | 230.625
Road (concrete) |  |  |  |  | 600 | m2 | New | Default |  | --Disposal Civil-- | Wogden Foot Access Road | 45917.6574 | 0 | Access Road | 75 | [5 empty] | SUB00524 | 1710 | 0 | 41402.4 | 30780000 | Road | 3857.6574 | 657.6 |  |  | 3.8577 | 0 | 45917.6574 | 45917.6574 | 0 | 41402.4 | 3857.6574 | 657.6 |  |  | 0 | 0 | 0
[14 empty] | Reinstatement & Demobilisation |  |  |  | 75
Crushed stone temporary access road |  |  |  |  | 4320 | m3 | New | Default |  | --Disposal Civil-- | TPT Diversion | 132685.7112 | 0 | Trans Pennine Trail Diversion | 540 | [5 empty] | SUB10519 | 7150 | 0 | 14256 | 926640000 | Road | 116135.7912 | 2293.92 |  |  | 116.1358 | 0 | 132685.7112 | 132685.7112 | 0 | 14256 | 116135.7912 | 2293.92 |  |  | 0 | 0 | 0
[14 empty] | Reinstatement & Demobilisation |  |  |  | 540
--Roads & Hardstandings-- | [5 empty] | n | --Source-- | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Roads & Hardstandings-- | [5 empty] | n | --Source-- | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Roads & Hardstandings-- | [5 empty] | n | --Source-- | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Steel Reinforcement (rebar) | [5 empty] | t | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB20697 | 1000 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Standard Strength Concrete Mixes-- | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB20121 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Standard Strength Concrete Mixes-- | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB20121 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Standard Strength Concrete Mixes-- | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB20121 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[14 empty] | 0 | [6 empty] | SUB00000
Temporary Roadways | [6 empty] | Origin | Transport Distance |  | End of Life | Comments | kgCO2 Added | kgCO2 Avoided | 0 | [6 empty] | 0
|  |  | Meters | Weeks | Quantity | Unit | Option | Mode | km | Option |  |  |  | 0 | [6 empty] | SUB00000
Temporary Roadway Metal Panels (2400x1200) |  |  |  |  | 0 | m x week | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | OHL00400 | 275 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Temporary Roadway Plastic Panels (2400x1200) |  |  |  |  | 0 | m x week | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | OHL00401 | 36 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[14 empty] | 0 | [6 empty] | SUB00000
Fence | [6 empty] | Origin | Transport Distance |  | End of Life | Comments | kgCO2 Added | kgCO2 Avoided | 0 | [6 empty] | SUB00000
Component |  |  |  |  | Quantity | Units | Option | Option | km | Option |  |  |  | 0 | [6 empty] | 0
Electric Double leaf Swing Gates |  |  |  |  | 1 | n | New | Road |  | --Disposal Civil-- | Wogden Foot | 4400 | 0 | Construction of SEC | 1 | [5 empty] | SUB00540 | 12567 | 0 | 4400 | 0 | Road | 0 | 0 |  |  | 0.047251 | 0 | 4400 | 4400 | 0 | 4400 | 0 | 0 |  |  | 0 | 0 | 0
Palisade Fence (2.425m high) |  |  |  |  | 194 | m | New | Default |  | --Disposal Civil-- | Wogden Foot | 47017.3208 | 0 | Construction of SEC | 16.1667 |  |  |  |  | 12m of fencing per load (3m width, four deep stacked) | SUB00529 | 361 | 0 | 46754 | 2101020 | Road | 263.3208 | 0 |  |  | 0.26332 | 0 | 47017.3208 | 47017.3208 | 0 | 46754 | 263.3208 | 0 |  |  | 0 | 0 | 0
Palisade Fence (2.425m high) |  |  |  |  | 95 | m | New | Default |  | --Disposal Civil-- | Yorkshire Water | 23023.9458 | 0 | Enabling works | 7.9167 | [5 empty] | SUB00529 | 361 | 0 | 22895 | 1028850 | Road | 128.9458 | 0 |  |  | 0.12895 | 0 | 23023.9458 | 23023.9458 | 0 | 22895 | 128.9458 | 0 |  |  | 0 | 0 | 0
Gates Double leaf swing (2.425m) |  |  |  |  | 2 | n | New | Default |  | --Disposal Civil-- | Yorkshire Water | 7385.5582 | 0 | Enabling works | 2 | [5 empty] | SUB00538 | 7992 | 0 | 7320 | 479520 | Road | 60.0982 | 5.46 |  |  | 0.060098 | 0 | 7385.5582 | 7385.5582 | 0 | 7320 | 60.0982 | 5.46 |  |  | 0 | 0 | 0
--Fence-- | [5 empty] | n | --Source-- | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Fence-- | [5 empty] | n | --Source-- | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Fence-- | [5 empty] | n | --Source-- | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[14 empty] | 0 | [6 empty] | SUB00000
Buildings and GIS foundations | [6 empty] | Origin | Transport Distance |  | End of Life | Comments | kgCO2 Added | kgCO2 Avoided | 0 | [6 empty] | SUB00000
Component |  |  |  |  | Quantity | Units | Option | Option | km | Option |  |  |  | 0 | [6 empty] | 0
GIS Building | [5 empty] | m2 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00248 | 2095.559 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
GIS Foundations only | [5 empty] | m2 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00275 | 2024.822 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Other buildings | [5 empty] | m2 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00249 | 2095.559 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[14 empty] | 0 | [6 empty] | SUB00000
Bunds and Transformer bunds | [6 empty] | Origin | Transport Distance |  | End of Life | Comments | kgCO2 Added | kgCO2 Avoided | 0 | [6 empty] | 0
Component |  |  |  |  | Quantity | Units | Option | Option | km | Option |  |  |  | 0 | [6 empty] | 0
Method 1: Specify the amounts of each material required for the bund(s) | [13 empty] | 0 | [6 empty] | SUB00000
--Standard Strength Concrete Mixes-- | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB20121 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Standard Strength Concrete Mixes-- | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB20121 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Standard Strength Concrete Mixes-- | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB20121 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Standard Strength Concrete Mixes-- | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB20121 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Steel Reinforcement (rebar) | [5 empty] | t | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB20697 | 1000 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Gravel | [5 empty] | kg | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB40002 | 1 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Formwork | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB30003 | 4569.14 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Method 2: estimate the bund size in m2 | [13 empty] | 0 | [6 empty] | SUB00000 | [14 empty] | 0 | 0 | 0
Standard Foundation above ground | [5 empty] | m2 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00270 | 3904.24 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Bund Foundations-- | [5 empty] | n | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Additional items | [6 empty] | Origin | Transport Distance |  | End of Life | Comments | kgCO2 Added | kgCO2 Avoided | 0 | [6 empty] | SUB00000 | [14 empty] | 0 | 0 | 0
Firewall (per m2) | [5 empty] | m2 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00575 | 1243.4 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Firewall Foundations (as bases) | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00576 | 2234.8 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Noise enclosure (brick) | [5 empty] | Item | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00577 | 461000 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Aquasentry Bund Pump (or Andil) | [5 empty] | n | --Source-- | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00578 | 42.3 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Auxilliary Transfer | [5 empty] | n | --Source-- | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00579 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Sheet piling and dewatering | [5 empty] | m2 | --Source-- | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00580 | 136 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Oil Containment tank | [5 empty] | n | --Source-- | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00581 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[14 empty] | 0 | [6 empty] | SUB00000
Trenches & Ducts | [6 empty] | Origin | Transport Distance |  | End of Life | Comments | kgCO2 Added | kgCO2 Avoided | 0 | [6 empty] | SUB00000
Component |  |  |  |  | Quantity | Units | Option | Option | km | Option |  |  |  | 0 | [6 empty] | 0
--Trenches & Ducts-- | [5 empty] | n | --Source-- | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Excavation |  |  |  |  | 11645 | m3 | New | Default |  | Recycled/Reuse |  | 95416.9174 | 0 | Cable Installation | 1455.625 |  |  |  |  | Based on full trench volume | SUB00374 | 1900 | 0 | 0 | 663765000 | Road | 83189.6674 | 12227.25 |  |  | 277.2989 | 0 | 95416.9174 | 95416.9174 | 0 | 0 | 83189.6674 | 12227.25 |  |  | 0 | 0 | 0
Ducts for power cable 200mm |  |  |  |  | 10350 | m | New | Default |  | --Disposal Civil-- |  | 38149.0965 | 0 | Cable Installation | 8.9844 |  |  |  |  | 192 6m duct runs per load | SUB00599 | 1.57 | 0 | 37593.27 | 487485 | Road | 61.0965 | 494.73 |  |  | 0.061096 | 0 | 38149.0965 | 38149.0965 | 0 | 37593.27 | 61.0965 | 494.73 |  |  | 0 | 0 | 0
Earth link pit |  |  |  |  | 2 | n | New | Default |  | --Disposal Civil-- |  | 2897.4865 | 0 | Cable Installation | 2 | [5 empty] | SUB00603 | 2325.4 | 0 | 2878.9 | 139524 | Road | 17.4865 | 1.1 |  |  | 0.017487 | 0 | 2897.4865 | 2897.4865 | 0 | 2878.9 | 17.4865 | 1.1 |  |  | 0 | 0 | 0
BT Ducts |  |  |  |  | 1875 | m | New | Default |  | --Disposal Civil-- |  | 7455.7347 | 0 | Cable Installation | 1.0417 |  |  |  |  | 300 6m duct runs per load | SUB00601 | 1.7 | 0 | 7354.125 | 95625 | Road | 11.9847 | 89.625 |  |  | 0.011985 | 0 | 7455.7347 | 7455.7347 | 0 | 7354.125 | 11.9847 | 89.625 |  |  | 0 | 0 | 0
Ducts for earthing copper 100mm diameter |  |  |  |  | 1875 | m | New | Default |  | --Disposal Civil-- |  | 6911.0682 | 0 | Cable Installation | 1.0417 |  |  |  |  | 300 6m duct runs per load | SUB00597 | 1.57 | 0 | 6810.375 | 88312.5 | Road | 11.0682 | 89.625 |  |  | 0.011068 | 0 | 6911.0682 | 6911.0682 | 0 | 6810.375 | 11.0682 | 89.625 |  |  | 0 | 0 | 0
--Trenches & Ducts-- | [5 empty] | n | --Source-- | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[14 empty] | 0 | [6 empty] | SUB00000
Cable Direct Burial - Excludes Cable | [6 empty] | Origin | Transport Distance |  | End of Life | Comments | kgCO2 Added | kgCO2 Avoided | 0 | [6 empty] | SUB00000
Estimate the materials required for direct burial of cables |  |  |  |  | Quantity | Unit | Option | Mode | km | Option |  |  |  | 0 | [6 empty] | SUB00000
Excavated material | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00393 | 1900 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
C12/15 Cem I |  |  |  |  | 2615 | m3 | New | Default |  | --Disposal Civil-- | CBS | 496715.4896 | 0 | Cable Installation | 326.875 | [5 empty] | SUB10670 | 2380 | 0 | 473315 | 186711000 | Road | 23400.4896 | 0 |  |  | 23.4005 | 0 | 496715.4896 | 496715.4896 | 0 | 473315 | 23400.4896 | 0 |  |  | 0 | 0 | 0
--Concrete Standard Strength-- | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | OHL10000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Concrete Standard Strength-- | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | OHL10000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Concrete Standard Strength-- | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | OHL10000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Rebar | [5 empty] | t | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB9002 | 1000 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Primary Sand | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB11660 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Ecosand | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB11661 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
MOT Type 1 Material | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00405 | 1990 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Filling with 6F2 Material | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00409 | 1554 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Alternativly provide lengths and cross-section size |  | Width | Depth | Length | Quantity | Unit | Option | Mode | km | Option |  |  |  | 0 | [6 empty] | SUB00000
Direct Buried Cable |  |  |  |  | 0 | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | OHL00740 | 1850 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Direct Buried Cable |  |  |  |  | 0 | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | OHL00740 | 1850 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Direct Buried Cable |  |  |  |  | 0 | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | OHL00740 | 1850 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Direct Buried Cable |  |  |  |  | 0 | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | OHL00740 | 1850 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[14 empty] | 0 | [6 empty] | SUB00000
Cable buried in Troughs - Excludes cable | [6 empty] | Origin | Transport Distance |  | End of Life | Comments | kgCO2 Added | kgCO2 Avoided | 0 | [6 empty] | SUB00000
Below ground trough |  |  |  |  | Quantity | Unit | Option | Mode | km | Option |  |  |  | 0 | [6 empty] | SUB00000
Base |  |  |  |  | 150 | m | New | Default |  | --Disposal Civil-- |  | 2954.4131 | 0 | Cable Installation | 12.5 |  |  |  |  | 12 per load | OHL10741 | 194 | 0 | 2845 | 873000 | Road | 109.4131 | 0 |  |  | 0.10941 | 0 | 2954.4131 | 2954.4131 | 0 | 2845 | 109.4131 | 0 |  |  | 0 | 0 | 0
Side walls |  |  |  |  | 150 | m | New | Default |  | --Disposal Civil-- |  | 5908.8262 | 0 | Cable Installation | 12.5 |  |  |  |  | 12 per load | OHL10742 | 388 | 0 | 5690 | 1746000 | Road | 218.8262 | 0 |  |  | 0.21883 | 0 | 5908.8262 | 5908.8262 | 0 | 5690 | 218.8262 | 0 |  |  | 0 | 0 | 0
Above ground trough |  |  |  |  | Quantity | Unit | Option | Mode | km | Option |  |  |  | 0 | [6 empty] | 0
Covers |  |  |  |  | 150 | m | New | Default |  | --Disposal Civil-- |  | 7990.5295 | 0 | Cable Installation | 12.5 |  |  |  |  | 12 per load | OHL10744 | 316.55 | 0 | 7812 | 1424475 | Road | 178.5295 | 0 |  |  | 0.17853 | 0 | 7990.5295 | 7990.5295 | 0 | 7812 | 178.5295 | 0 |  |  | 0 | 0 | 0
[14 empty] | 0 | [6 empty] | SUB00000
Cable tunneled sections - Excludes cable | [6 empty] | Origin | Transport Distance |  | End of Life | Comments | kgCO2 Added | kgCO2 Avoided | 0 | [6 empty] | SUB00000
Estimate the materials required for direct burial of cables |  |  |  |  | Quantity | Unit | Option | Mode | km | Option |  |  |  | 0 | [6 empty] | SUB00000
Excavated material | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00393 | 1900 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Concrete Standard Strength-- | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | OHL10000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Concrete Standard Strength-- | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | OHL10000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Concrete Standard Strength-- | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | OHL10000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Concrete Standard Strength-- | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | OHL10000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Rebar | [5 empty] | t | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB9002 | 1000 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Primary Sand | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB11660 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Ecosand | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB11661 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
MOT Type 1 Material | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00405 | 1990 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Filling with 6F2 Material | [5 empty] | m3 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00409 | 1554 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Tunnel boring machine | [5 empty] | m | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | OHL10000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Standard Tunnel Sections |  |  |  |  | Quantity | Unit | Option | Mode | km | Option |  |  |  | 0 | [6 empty] | SUB00000
--Tunnel sections-- | [5 empty] | m | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | OHL10000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Tunnel sections-- | [5 empty] | m | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | OHL10000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Tunnel sections-- | [5 empty] | m | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | OHL10000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Tunnel sections-- | [5 empty] | m | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | OHL10000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Tunnel sections-- | [5 empty] | m | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | OHL10000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[14 empty] | 0 | [6 empty] | SUB00000
Drainage | [6 empty] | Origin | Transport Distance |  | End of Life | Comments | kgCO2 Added | kgCO2 Avoided | 0 | [6 empty] | SUB00000
Component |  |  |  |  | Quantity | Units | Option | Option | km | Option |  |  |  | 0 | [6 empty] | 0
Soakaway Small |  |  |  |  | 4 | n | New | Default |  | --Disposal Civil-- | Estimated for Wogden Foot and windell edge haul road | 7250.9595 | 0 | Enabling works |  |  | 1 |  |  |  | SUB00615 | 6048 | 0 | 7160 | 725760 | Road | 90.9595 | 0 |  |  | 0.09096 | 0 | 7250.9595 | 7250.9595 | 0 | 7160 | 90.9595 | 0 |  |  | 0 | 0 | 0
Land drainage channels |  |  |  |  | 1200 | m | New | Default |  | --Disposal Civil-- | Windell Edge Haul Road | 7263.6115 | 0 | Enabling works | 10 | [5 empty] | SUB00611 | 304 | 0 | 5892 | 10944000 | Road | 1371.6115 | 0 |  |  | 1.3716 | 0 | 7263.6115 | 7263.6115 | 0 | 5892 | 1371.6115 | 0 |  |  | 0 | 0 | 0
--Drainage-- | [5 empty] | n | --Source-- | Default | 100 | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Drainage-- | [5 empty] | n | --Source-- | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Drainage-- | [5 empty] | n | --Source-- | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Drainage-- | [5 empty] | n | --Source-- | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Drainage-- | [5 empty] | n | --Source-- | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[8 empty] | n | [5 empty] | 0 | [6 empty] | SUB00000
Underground Earthing | [6 empty] | Origin | Transport Distance |  | End of Life | Comments | kgCO2 Added | kgCO2 Avoided | 0 | [6 empty] | SUB00000
Component |  |  |  |  | Quantity | Units | Option | Option | km | Option |  |  |  | 0 | [6 empty] | 0
Earthing tape 50mmx6mm (inc. Excav Backfill & Topsoil) |  |  |  |  | 125 | m | New | Default |  | --Disposal Civil-- | TBC in detailed design phase | 1682.6458 | 0 | Construction of SEC |  |  | 2 |  |  |  | SUB00621 | 2.68 | 0 | 1681.3863 | 10050 | Road | 1.2596 | 0 |  |  | 0.0012596 | 0 | 1682.6458 | 1682.6458 | 0 | 1681.3863 | 1.2596 | 0 |  |  | 0 | 0 | 0
To PI's, CVT's, CT's, SA's and ES's |  |  |  |  | 72 | m | New | Default |  | --Disposal Civil-- | 2 No. 2m tapes for 18 bitso f equipment | 969.204 | 0 | Construction of SEC |  |  | 2 |  |  |  | SUB00625 | 2.68 | 0 | 968.4785 | 5788.8 | Road | 0.72551 | 0 |  |  | 0.00072551 | 0 | 969.204 | 969.204 | 0 | 968.4785 | 0.72551 | 0 |  |  | 0 | 0 | 0
To Ham Units, Gantries and Pantographs |  |  |  |  | 64 | m | New | Default | 40 | --Disposal Civil-- | 8No. 8m connections to gantries | 861.5147 | 0 | Construction of SEC |  |  | 2 |  |  |  | SUB00626 | 2.68 | 0 | 860.8698 | 5145.6 | Road | 0.6449 | 0 |  |  | 0.0006449 | 0 | 861.5147 | 861.5147 | 0 | 860.8698 | 0.6449 | 0 |  |  | 0 | 0 | 0
--Earthing-- | [5 empty] | m | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00622 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
--Earthing-- | [5 empty] | m | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | [6 empty] | SUB00622 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Joints (1 No. per 5m of total tape + No. earth rods) |  |  |  |  | 120 | n | New | Default |  | --Disposal Civil-- |  | 2.916 | 0 | Cable Installation |  |  | 2 |  |  |  | SUB00631 | 0 | 0 | 2.916 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 2.916 | 2.916 | 0 | 2.916 | 0 | 0 |  |  | 0 | 0 | 0
Earthing rods (Length x number) |  |  |  |  | 30 | m | New | Default |  | --Disposal Civil-- | Estimated 6 No. 5m | 131.8818 | 0 | Cable Installation |  |  | 2 |  |  |  | SUB00632 | 1.818 | 0 | 131.6767 | 1636.2 | Road | 0.20506 | 0 |  |  | 0.00020506 | 0 | 131.8818 | 131.8818 | 0 | 131.6767 | 0.20506 | 0 |  |  | 0 | 0 | 0
[14 empty] | 0 | [6 empty] | SUB00000
Lighting | [6 empty] | Origin | Transport Distance |  | End of Life | Comments | kgCO2 Added | kgCO2 Avoided | 0 | kgCO2 Avoided |  | kgCO2 Avoided |  |  |  | SUB00000
Component |  |  |  |  | Quantity | Units | Option | Option | km | Option |  |  |  | 0 | [6 empty] | 0
Lighting (incl. foundation base, lighting column, fittings & connections) | [5 empty] | n | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00636 | 2170 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Lighting (incl. foundation base, lighting column, fittings & connections) | [5 empty] | n | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00636 | 2170 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[14 empty] | 0 | [6 empty] | SUB00000
Services | [6 empty] | Origin | Transport Distance |  | End of Life | Comments | kgCO2 Added | kgCO2 Avoided | 0 | kgCO2 Avoided |  | kgCO2 Avoided |  |  |  | 0
Component |  |  |  |  | Quantity | Units | Option | Option | km | Option |  |  |  | 0 | [6 empty] | 0
Water main u/g pipework | [5 empty] | m | --Source-- | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00639 | 1.03 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Water main connection | [5 empty] | n | --Source-- | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00640 | 262 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Braithwaite 120,000 litre incl found, support walls, paint | [5 empty] | n | --Source-- | Default | 500 | --Disposal Civil-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00641 | 67604.64 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Fire Hydrant No. | [5 empty] | n | --Source-- | Default | 4 | --Disposal Civil-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00642 | 269.3 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Fire Hydrant pipework | [5 empty] | m | --Source-- | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00643 | 1.03 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Diesel Generator Bund | [5 empty] | m2 | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00644 | 1756.8886 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[14 empty] | 0 | [6 empty] | SUB00000
Site energy - estimated consumption over life of scheme construction | [6 empty] | Origin | Transport Distance |  | End of Life | Comments | kgCO2 Added | kgCO2 Avoided | 0 | kgCO2 Avoided |  | kgCO2 Avoided |  |  |  | SUB00000 | [12 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Item Name |  |  |  |  | Quantity | Unit | Option | Mode | km | Option |  |  |  | 0 | [6 empty] | SUB00000 | [12 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Mains electricity | [5 empty] | kWh | [5 empty] | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 |  | 0 | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Renewable electricity | [5 empty] | kWh | [5 empty] | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 |  | 0 | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Diesel | [5 empty] | litres |  | Default | 500 |  |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Biodiesel | [5 empty] | litres |  | Default |  |  |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[14 empty] | 0 | [6 empty] | SUB00000 | [12 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Other items | [6 empty] | Origin | Transport Distance |  | End of Life | Comments | kgCO2 Added | kgCO2 Avoided | 0 | kgCO2 Avoided |  | kgCO2 Avoided |  |  |  | SUB00000 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Component |  |  |  |  | Quantity | Units | Option | Option | km | Option |  |  |  | 0 | [6 empty] | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
General concrete | [6 empty] | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
General steel | [6 empty] | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
General transport (e.g. materials from other sites) | [6 empty] | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
General aggregates | [6 empty] | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
General brick | [6 empty] | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
General paint | [6 empty] | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
General wood | [6 empty] | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Galvanised steel | [6 empty] | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB10001 | 1000 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
General aluminium | [6 empty] | New | Default |  | --Disposal Civil-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 | 0 | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[14 empty] | 0 | [6 empty] | SUB00000
Additional Items | [6 empty] | Origin | Transport Distance |  | End of Life | Comments | kgCO2 Added | kgCO2 Avoided | 0 | kgCO2 Avoided |  | kgCO2 Avoided |  |  |  | SUB00000
Item Name |  |  | Total Weight (kg) | kgCO2e EF/unit | Quantity | Units | Option | Option | km | Option |  |  |  | 0 | [6 empty] | SUB00000
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  | SUB00000 | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  |  | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  |  | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  |  | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  |  | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  |  | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  |  | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  |  | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  |  | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  |  | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  |  | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  |  | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  |  | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  |  | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  |  | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[7 empty] | New | Road | 30 | --Disposal-- |  | 0 | 0 | 0 | 0 |  | #REF! |  |  |  |  | 0 | 0 |  | 0 | Road | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Bridge sections - permanent | [13 empty] | Permanent Bridge | 4 |  |  |  |  | Bridge permanent - allow 4 movements
Bridge sections - temporary | [13 empty] | Temporary Bridge | 15 |  |  | 15 |  | Bridge temporary - allow 12 movements for sections, plus 3 loads for decks, etc.
Steelwork - tunnel | [13 empty] | Reinstatement & Demobilisation | 8 |  |  | 4 |  | Steelwork for tunnel - 4 loads to remove, 8 to supply