## Gantt Chart
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | Ashroyd Business Park |  |  |  | CNS | 318709
|  | Cost | DFE's |  | Desk Request
Enter Company Name in cell B2. |  | 0 |  | Start Date |  | End Date | Matt Cumpsy
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3. |  |  |  | 2019-06-10
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  |  | Show Me week | 1 |  |  | Note DFE provison of £2000 worked into qoute as requested by customer | 2019-06-10 | [6 empty] | 2019-06-17 | [6 empty] | 2019-06-24 | [6 empty] | 2019-07-01 | [6 empty] | 2019-07-08 | [6 empty] | 2019-07-15 | [6 empty] | 2019-07-22 | [6 empty] | 2019-07-29 | [6 empty] | 2019-08-05 | [6 empty] | 2019-08-12 | [6 empty] | 2019-08-19 | [6 empty] | 2019-08-26 | [6 empty] | 2019-09-02 | [6 empty] | 2019-09-09 | [6 empty] | 2019-09-16 | [6 empty] | 2019-09-23 | [6 empty] | 2019-09-30 | [6 empty] | 2019-10-07 | [6 empty] | 2019-10-14 | [6 empty] | 2019-10-21 | [6 empty] | 2019-10-28 | [6 empty] | 2019-11-04 | [6 empty] | 2019-11-11 | [6 empty] | 2019-11-18 | [6 empty] | 2019-11-25 | [6 empty] | 2019-12-02
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2019-06-10 to 2019-12-08
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | Phase | Estimate | PROGRESS | START | END | STATUS | Notes | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule.
| Phase 1 Cable TR&R | WALDLU3R | 0% |  | TBC |  | PHASE 1 TEST ROD WALDLU3R ECD 05/07 | 2019-06-10: 1; 2019-06-11: 1; 2019-06-12: 1; 2019-06-13: 1; 2019-06-14: 1; 2019-06-15: 1; 2019-06-16: 1; 2019-06-17: 2; 2019-06-18: 2; 2019-06-19: 2; 2019-06-20: 2; 2019-06-21: 2; 2019-06-22: 2; 2019-06-23: 2; 2019-06-24: 2; 2019-06-25: 2; 2019-06-26: 2; 2019-06-27: 2; 2019-06-28: 2; 2019-06-29: 2; 2019-06-30: 2; 2019-07-01: 2; 2019-07-02: 2; 2019-07-03: 2; 2019-07-04: 2; 2019-07-05: 2
| PHASE 2 CIVILS | WALDM53J | 0% |  | TBC |  | PHASE 2 CIVILS WALDM53J ECD 16/07 | 2019-06-10: 1; 2019-06-11: 1; 2019-06-12: 1; 2019-06-13: 1; 2019-06-14: 1; 2019-06-15: 1; 2019-06-16: 1; 2019-06-17: 2; 2019-06-18: 2; 2019-06-19: 2; 2019-06-20: 2; 2019-06-21: 2; 2019-06-22: 2; 2019-06-23: 2; 2019-06-24: 2; 2019-06-25: 2; 2019-06-26: 2; 2019-06-27: 2; 2019-06-28: 2; 2019-06-29: 2; 2019-06-30: 2; 2019-07-01: 2; 2019-07-02: 2; 2019-07-03: 2; 2019-07-04: 2; 2019-07-05: 2; 2019-07-06: 2; 2019-07-07: 2; 2019-07-08: 2; 2019-07-09: 2; 2019-07-10: 2; 2019-07-11: 2; 2019-07-12: 2; 2019-07-13: 2; 2019-07-14: 2; 2019-07-15: 2; 2019-07-16: 2
| Phase 3 Fibre |  | 0% |  | TBC |  | FIBRES ESTIMATE: WALEH35G - RBD 21/08/19 | 2019-06-10: 1; 2019-06-11: 1; 2019-06-12: 1; 2019-06-13: 1; 2019-06-14: 1; 2019-06-15: 1; 2019-06-16: 1; 2019-06-17: 2; 2019-06-18: 2; 2019-06-19: 2; 2019-06-20: 2; 2019-06-21: 2; 2019-06-22: 2; 2019-06-23: 2; 2019-06-24: 2; 2019-06-25: 2; 2019-06-26: 2; 2019-06-27: 2; 2019-06-28: 2; 2019-06-29: 2; 2019-06-30: 2; 2019-07-01: 2; 2019-07-02: 2; 2019-07-03: 2; 2019-07-04: 2; 2019-07-05: 2; 2019-07-06: 2; 2019-07-07: 2; 2019-07-08: 2; 2019-07-09: 2; 2019-07-10: 2; 2019-07-11: 2; 2019-07-12: 2; 2019-07-13: 2; 2019-07-14: 2; 2019-07-15: 2; 2019-07-16: 2; 2019-07-17: 2; 2019-07-18: 2; 2019-07-19: 2; 2019-07-20: 2; 2019-07-21: 2; 2019-07-22: 2; 2019-07-23: 2; 2019-07-24: 2; 2019-07-25: 2; 2019-07-26: 2; 2019-07-27: 2; 2019-07-28: 2; 2019-07-29: 2; 2019-07-30: 2; 2019-07-31: 2; 2019-08-01: 2; 2019-08-02: 2; 2019-08-03: 2; 2019-08-04: 2; 2019-08-05: 2; 2019-08-06: 2; 2019-08-07: 2; 2019-08-08: 2; 2019-08-09: 2; 2019-08-10: 2; 2019-08-11: 2; 2019-08-12: 2; 2019-08-13: 2; 2019-08-14: 2; 2019-08-15: 2; 2019-08-16: 2; 2019-08-17: 2; 2019-08-18: 2; 2019-08-19: 2; 2019-08-20: 2; 2019-08-21: 2
| Phase 4 Cable | WALDMH5D | 0% |  |  |  | PHASE 4 COPPER WALDMH5D ECD 25/07 | 2019-06-10: 1; 2019-06-11: 1; 2019-06-12: 1; 2019-06-13: 1; 2019-06-14: 1; 2019-06-15: 1; 2019-06-16: 1; 2019-06-17: 2; 2019-06-18: 2; 2019-06-19: 2; 2019-06-20: 2; 2019-06-21: 2; 2019-06-22: 2; 2019-06-23: 2; 2019-06-24: 2; 2019-06-25: 2; 2019-06-26: 2; 2019-06-27: 2; 2019-06-28: 2; 2019-06-29: 2; 2019-06-30: 2; 2019-07-01: 2; 2019-07-02: 2; 2019-07-03: 2; 2019-07-04: 2; 2019-07-05: 2; 2019-07-06: 2; 2019-07-07: 2; 2019-07-08: 2; 2019-07-09: 2; 2019-07-10: 2; 2019-07-11: 2; 2019-07-12: 2; 2019-07-13: 2; 2019-07-14: 2; 2019-07-15: 2; 2019-07-16: 2; 2019-07-17: 2; 2019-07-18: 2; 2019-07-19: 2; 2019-07-20: 2; 2019-07-21: 2; 2019-07-22: 2; 2019-07-23: 2; 2019-07-24: 2; 2019-07-25: 2
0%
| Stores to site needed |  | 100% |  |  |  | stores conifmed delivered 17/6/19
0%
Legend
[6 empty] | 1 | With planning (i.e est creation, job pack build)
[6 empty] | 2 | Dwell (i.e with contractor/Dl to programme
[6 empty] | 3 | Planned
[6 empty] | 4 | Completed
[6 empty] | 5 | Customer Dwell
Simple Project Overview
Civils
Fibre route and TR&T
Note on P7: Tyler,TM,Tim,BWA423 R: Handover Date

## SOW
Stores required to site
Duct 54 = 350M, 90-degree bends = 10, 45-degree bends = 10, JUF4 frame & Lids = 5, Draw rope = 2
SOW
A total of five new units are going to be built with the developer laying duct 54 on his land.
NIA Copper & Fibre required to each unit. PCP35 & Node TABYQ to be used.
Phase 1 Cable TR&R
The fibre duct route appears to be very congested and requires a TR&R. this was agreed with CFM Richard Goodison on the JV.
From the Node TABYQ to the new JMF6 is a distance of 950M. No TM is required along this route
Node grid ref is SE 36983 01627
Phase 2 Civils
In the entrance to unit Store First is an existing JUF4 in the grass verge. Grid ref SE 36610 01297
A single duct 54 core drill is required and 9M of duct 54 in carriageway to the developer’s boundary.
Steel plates will be required to maintain access 24/7 to this unit while digging. This will serve the standalone unit.
Where the other four units are going to be built, brand new, never used duct 54 & JUF6 exist.
This existing JUF6 will be in the way of the new entrance so a new JMF6 will be required further down the road.
Build new JMF6 over existing two-way duct 54 in footway at grid ref SE 36473 01215.
Leave a 1M two-way poke out towards site for the developer to link to.
Also required in this new JMF6 is a 7M road crossing and 2M in footway, to the opposite side of the road footway.
Build a new JMF6 here at grid ref SE 36473 01214 in the footway. Provide a 1M two-way duct 54 poke out.
This new JMF6 will feed future units in a different phase of the development works.
No TM will be required at this stage as still a greenfield site. Requirements may change if development starts.
Phase 3 Fibre
D/I 1,000M of subduct mono-bore N0.5 from Node TABYQ to the new JMF6 at grid ref SE 36473 01215
Blow on 1,000M of COF200/48F from Node TABYQ to the new JMF6 at grid ref SE 36473 01215. Leave 10M coil at node position
Create a medium size node to feed the units
The ports on the Node TABYQ looked full, engineer to asses on installation visit.
From this node a COF250/12F will be required to all five new units, a total of 600M
Four units will feed in the same direction, but the standalone unit will feed back on its self towards PCP35.
Present the COF250/12F on an MCB in each unit where the duct 54 enters the office area. surveyed from plans.
Phase 4 Cable
D/I 200M of 50/0.5 PET from PCP35 to the new JMF6 / Node location and create a network joint.
Plenty of room in PCP35 to terminate.
From the network 50pr joint provide a 20/0.5 PET cable to each unit and present on a BC201D. 500M required for all units.
Supply each unit with 10 new D sides and record.
For the stand-alone unit next to PCP35 D/I a 20/0.5 PET direct from PCP35 (200M) and terminate on a BC201D.
Record all new D sides used on a A154.
Please note at the time of this survey no building work had started.
All cable distance onto site are estimated.

## DFE's
Customer Paid DFE's
DFE Date | ESTIMATE | Synthetics | Quantity | Description | Cost Per Unit | Total | Insert rows above total lines as required
0
Openreach Covered DFE's
DFE Date | Estimate | Synthetic Code | Qty | Description | Unit Price | Total
0
[5 empty] | Total | 0